## README
Finvasia PT-R&R Platform - Corrected Source Data
Prepared 29-Sep-2026, extended 08-Oct-2026, from: Organizational_Chart (23-Aug-26), Project_Tracker (Rest, Shoonya), R_R_Parameters_2, RACI, RCA
As-of date used for overdue checks | 2026-09-29
Sheet | What it contains
Employee_Master | Every box from the 17 visible org-chart sheets as one row. Proposed record IDs (EMP-/POS-), cleaned name and designation, reporting manager, proposed login role, and data-quality flags. The 2 hidden sheets (Prodduct, Product-Shoonya) are outdated copies and were NOT imported.
Name_Collisions | Names shared by more than one record. Each must be confirmed against HRMS before import.
Departments | Canonical department list, head, live headcount, proposed performance category, and the tracker aliases that map to it.
Category_Weights | Corrected metric weights per team category. Every column must total 100% (check row).
Tracker_Cleaned | Original 115 tracker rows split to one row per task x assignee, with resolved Employee IDs, mapped statuses, classified blockers and derived timing (formulas).
Project_Register | One row per project with proposed PRJ IDs and live task counts.
OnTime_Recalc | On-time rate recalculated with the corrected eligibility rules, beside the value the old sheet produced.
Issue_Register | Every issue found in the five source files, with severity and the fix applied.
Workflow_Templates | RACI.xlsx turned into a reusable "Email campaign" project template: one row per step with R / A / C / I, checklist, reviewer, required evidence, SLA in business days and effort. Conflicts between the two versions in the source are flagged.
Risk_Register | Risks from RACI.xlsx, one per row, linked to the template step, with criticality, dependencies, assumptions, mitigation and new owner / status / review-date fields.
RCA_Register | Incident root-cause log built from RCA.xlsx (which had headers only). Fill one row per incident; grey columns are formulas. Header comments show which source column each field came from. Row 2 is an example to replace or delete.
Colour key | Yellow cells = input needed from you / HR (e.g. HRMS code, priority). Pink cells = flagged for confirmation. Black text = formulas; do not overwrite.
ID note | EMP-/POS-/PRJ- IDs are placeholders so the data can be linked now. Replace EMP IDs with official HRMS employee codes before go-live; the HRMS column is provided for that.

## Employee_Master
Record ID | HRMS Emp Code (fill) | Record Type | Full Name | Designation | Department | Level in Chart | Reporting Manager ID | Reporting Manager | Direct Reports | Proposed Platform Role | Flags / To Confirm | Original Chart Text
POS-0001 |  | Vacant Position | (vacant) | Managing Director | AI | 1 |  |  | 7 | None (vacant) | Vacant / unnamed position | Managing Director
EMP-0002 |  | Employee | Anudesh Saini | Machine Learning Engineer | AI | 2 | POS-0001 | Managing Director | 4 | Manager |  | Anudesh Saini (Machine Learning Engineer)
EMP-0003 |  | Employee | Mukund Madhav | Data Engineer | AI | 3 | EMP-0002 | Anudesh Saini | 1 | Manager |  | Mukund Madhav (Data Engineer)
EMP-0004 |  | Employee | Piyush Chhabra | Data Engineer | AI | 4 | EMP-0003 | Mukund Madhav | 0 | None (employee record) |  | Piyush Chhabra (Data Engineer)
EMP-0005 |  | Employee | Chetan Sharma | AI Engineer | AI | 3 | EMP-0002 | Anudesh Saini | 2 | Manager |  | Chetan Sharma (AI Engineer)
EMP-0006 |  | Employee | Divyanshu | Jr. ML Ops Engineer | AI | 4 | EMP-0005 | Chetan Sharma | 0 | None (employee record) | Single name only - add surname | Divyanshu (Jr. ML Ops Engineer)
EMP-0007 |  | Employee | Nikhal Kumar Rana | Associate AI Engineer | AI | 4 | EMP-0005 | Chetan Sharma | 0 | None (employee record) |  | Nikhal Kumar Rana (Associate AI Engineer)
EMP-0008 |  | Employee | Ankit Sharma | Data Analyst | AI | 3 | EMP-0002 | Anudesh Saini | 0 | None (employee record) |  | Ankit Sharma (Data Analyst)
EMP-0009 |  | Employee | Rajat Sharma | Sr. AI Engineer | AI | 3 | EMP-0002 | Anudesh Saini | 3 | Manager |  | Rajat Sharma (Sr. AI Engineer)
EMP-0010 |  | Employee | Sameep Rohilla | Jr. AI Engineer | AI | 4 | EMP-0009 | Rajat Sharma | 0 | None (employee record) |  | Sameep Rohilla (Jr. AI Engineer)
EMP-0011 |  | Employee | Ishan Singla | Jr. ML Ops Engineer | AI | 4 | EMP-0009 | Rajat Sharma | 0 | None (employee record) |  | Ishan Singla (Jr. ML Ops Engineer)
EMP-0012 |  | Employee | Kunal Mehra | Jr. AI Engineer | AI | 4 | EMP-0009 | Rajat Sharma | 0 | None (employee record) |  | Kunal Mehra (Jr. AI Engineer)
POS-0001 |  | Vacant Position | (vacant) | Managing Director | Product | 1 |  |  | 7 | None (vacant) | Vacant / unnamed position | Managing Director
EMP-0014 |  | Employee | Vishal Sharma | Lead QA | Product | 2 | POS-0001 | Managing Director | 1 | Team Lead |  | Vishal Sharma (Lead QA)
EMP-0015 |  | Employee | Amit Kumar | Sr. QA Engineer | Product | 3 | EMP-0014 | Vishal Sharma | 4 | Manager | Name shared with another record - confirm identity | Amit Kumar (Sr. QA Engineer)
EMP-0016 |  | Employee | Pankaj Kumar | QA Engineer | Product | 4 | EMP-0015 | Amit Kumar | 0 | None (employee record) |  | Pankaj Kumar (QA Engineer)
EMP-0017 |  | Employee | Deepti Sharma | QA Engineer | Product | 4 | EMP-0015 | Amit Kumar | 0 | None (employee record) |  | Deepti Sharma (QA Engineer)
EMP-0018 |  | Employee | Navdeep Thakur | QA Engineer | Product | 4 | EMP-0015 | Amit Kumar | 0 | None (employee record) |  | Navdeep Thakur (QA Engineer)
EMP-0019 |  | Employee | Vipul Mahajan | QA Engineer | Product | 4 | EMP-0015 | Amit Kumar | 0 | None (employee record) |  | Vipul Mahajan (QA Engineer)
EMP-0020 |  | Employee | Deepinder Singh | Sr. Project Manager | Product | 2 | POS-0001 | Managing Director | 16 | Manager |  | Deepinder Singh (Sr. Project Manager)
EMP-0021 |  | Employee | Rajan Kumar | Project Manager | Product | 3 | EMP-0020 | Deepinder Singh | 1 | Manager |  | Rajan Kumar (Project Manager)
EMP-0022 |  | Employee | Geetankshi | Associate Project Coordinator | Product | 4 | EMP-0021 | Rajan Kumar | 0 | None (employee record) | Single name only - add surname | Geetankshi (Associate Project coordinater)
EMP-0023 |  | Employee | Sparsh Choudhary | Sr. Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Sparsh Choudhary (Sr. Software Engineer)
EMP-0024 |  | Employee | Sumit Roy | Associate Product Manager | Product | 3 | EMP-0020 | Deepinder Singh | 5 | Manager |  | Sumit Roy (Associate Product Manager)
EMP-0025 |  | Employee | Manisha Kumari | Business Analyst | Product | 4 | EMP-0024 | Sumit Roy | 0 | None (employee record) |  | Manisha Kumari (Business Analyst)
EMP-0026 |  | Employee | Sukriti | Business Analyst | Product | 4 | EMP-0024 | Sumit Roy | 0 | None (employee record) | Single name only - add surname | Sukriti (Business Analyst)
EMP-0027 |  | Employee | Aryan Raj | Business Analyst | Product | 4 | EMP-0024 | Sumit Roy | 0 | None (employee record) |  | Aryan Raj (Business Analyst)
EMP-0028 |  | Employee | Siddhant Sharma | Team Lead-API | Product | 4 | EMP-0024 | Sumit Roy | 0 | None (employee record) |  | Siddhant Sharma (Team Lead-API)
EMP-0029 |  | Employee | Saurav Sharma | API Integration Analyst | Product | 4 | EMP-0024 | Sumit Roy | 2 | Manager |  | Saurav Sharma (API Integration Analyst)
EMP-0030 |  | Employee | Avinash Rai | API Support & Tech. Analyst | Product | 5 | EMP-0029 | Saurav Sharma | 0 | None (employee record) | Chart text malformed (fixed) | Avinash Rai (API Support & Tech. Analyst))
EMP-0031 |  | Employee | Ashok Sharma | API Support & Tech. Analyst | Product | 5 | EMP-0029 | Saurav Sharma | 0 | None (employee record) | Chart text malformed (fixed) | Ashok Sharma (API Support & Tech. Analyst))
EMP-0032 |  | Employee | Ravi Beniwal | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Ravi Beniwal (Software Engineer)
EMP-0033 |  | Employee | Rakhi | Sr. Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Single name only - add surname | Rakhi (Sr. Software Engineer)
EMP-0034 |  | Employee | Lucky Bawa | Sr. Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Lucky Bawa (Sr. Software Engineer)
EMP-0035 |  | Employee | Virendra Nishad | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Virendra Nishad (Software Engineer)
EMP-0036 |  | Employee | Pawan Kumar | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Name shared with another record - confirm identity | Pawan Kumar (Sofwtare Engineer)
EMP-0037 |  | Employee | Ankush | Sr. Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Single name only - add surname | Ankush (Sr. Software Engineer)
EMP-0038 |  | Employee | Muskan | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Name shared with another record - confirm identity; Single name only - add surname | Muskan (Sofwate Engineer)
EMP-0039 |  | Employee | Avinash | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Single name only - add surname | Avinash (Software Engineer)
EMP-0040 |  | Employee | Kartik Sharma | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Kartik Sharma (Software Engineer)
EMP-0041 |  | Employee | Ankit | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Name shared with another record - confirm identity; Single name only - add surname | Ankit (Software Engineer)
EMP-0042 |  | Employee | Shivam | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) | Single name only - add surname | Shivam (Software Engineer)
EMP-0043 |  | Employee | Paramjit Singh | Word Press Developer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Paramjit Singh(Word Press Developer)
EMP-0044 |  | Employee | Mayank Kumar | Software Engineer | Product | 3 | EMP-0020 | Deepinder Singh | 0 | None (employee record) |  | Mayank Kumar (Software Engineer)
EMP-0045 |  | Employee | Randhir Kumar | Sr. Project Manager | Product | 2 | POS-0001 | Managing Director | 2 | Manager |  | Randhir Kumar (Sr. Project Manager)
EMP-0046 |  | Employee | Jatin Vashisht | iOS Manager | Product | 3 | EMP-0045 | Randhir Kumar | 5 | Manager | Chart text malformed (fixed) | Jatin Vashisht (iOS Manager:
EMP-0047 |  | Employee | Akshay A Walia | Sr. Software Engineer | Product | 4 | EMP-0046 | Jatin Vashisht | 0 | None (employee record) |  | Akshay A Walia (Sr. Software Engineer)
EMP-0048 |  | Employee | Saksham | Software Engineer | Product | 4 | EMP-0046 | Jatin Vashisht | 0 | None (employee record) | Single name only - add surname | Saksham (Software Engineer)
EMP-0049 |  | Employee | Vinay Dhayani | Software Engineer | Product | 4 | EMP-0046 | Jatin Vashisht | 0 | None (employee record) |  | Vinay Dhayani (Software Engineer)
EMP-0050 |  | Employee | Akash Bansal | Software Engineer | Product | 4 | EMP-0046 | Jatin Vashisht | 1 | Manager | Chart text malformed (fixed) | Akash Bansal Software Engineer)
EMP-0051 |  | Employee | Payal Dhiman | Software Engineer | Product | 5 | EMP-0050 | Akash Bansal | 0 | None (employee record) |  | Payal Dhiman (Software Engineer)
EMP-0052 |  | Employee | Tushar Verma | Software Engineer | Product | 4 | EMP-0046 | Jatin Vashisht | 0 | None (employee record) | Chart text malformed (fixed) | Tushar Verma Software Engineer)
EMP-0053 |  | Employee | Rupinder Kaur | Android Manager | Product | 3 | EMP-0045 | Randhir Kumar | 5 | Manager |  | Rupinder Kaur (Android Manager)
EMP-0054 |  | Employee | Keshav Bansal | Sr Software Engineer | Product | 4 | EMP-0053 | Rupinder Kaur | 0 | None (employee record) |  | Keshav Bansal (Sr Software Engineer)
EMP-0055 |  | Employee | Ankit Singh | Software Engineer | Product | 4 | EMP-0053 | Rupinder Kaur | 0 | None (employee record) |  | Ankit SIngh ( Software Engineer)
EMP-0056 |  | Employee | Manthan Mahajan | Software Engineer | Product | 4 | EMP-0053 | Rupinder Kaur | 0 | None (employee record) |  | Manthan Mahajan (Software Engineer)
EMP-0057 |  | Employee | Sumit Kumar | Sr. Software Engineer | Product | 4 | EMP-0053 | Rupinder Kaur | 1 | Manager |  | Sumit Kumar (Sr. Software Engineer)
EMP-0058 |  | Employee | Jaspreet Singh | Software Engineer | Product | 5 | EMP-0057 | Sumit Kumar | 0 | None (employee record) |  | Jaspreet Singh (Software Engineer)
EMP-0059 |  | Employee | Arun Chauhan | Android Developer | Product | 4 | EMP-0053 | Rupinder Kaur | 0 | None (employee record) |  | Arun Chauhan (Android Developer)
EMP-0060 |  | Employee | Kapil Kumar | Sr. BA | Product | 2 | POS-0001 | Managing Director | 6 | Manager |  | Kapil Kumar (Sr. BA)
EMP-0061 |  | Employee | Deepali Mittal | BA | Product | 3 | EMP-0060 | Kapil Kumar | 1 | Manager |  | Deepali Mittal (BA)
EMP-0062 |  | Employee | Hani Tomar | BA | Product | 4 | EMP-0061 | Deepali Mittal | 0 | None (employee record) |  | Hani Tomar (BA)
EMP-0063 |  | Employee | Surabhi Abrol | BA | Product | 3 | EMP-0060 | Kapil Kumar | 1 | Manager |  | Surabhi Abrol (BA)
EMP-0064 |  | Employee | Ansh Arora | Associate BA | Product | 4 | EMP-0063 | Surabhi Abrol | 0 | None (employee record) |  | Ansh Arora (Associate BA)
EMP-0065 |  | Employee | Aakash Thakur | BA | Product | 3 | EMP-0060 | Kapil Kumar | 0 | None (employee record) |  | Aakash Thakur (BA)
EMP-0066 |  | Employee | Rafay Saifi | BA | Product | 3 | EMP-0060 | Kapil Kumar | 0 | None (employee record) |  | Rafay Saifi (BA)
EMP-0067 |  | Employee | Sonia | BA | Product | 3 | EMP-0060 | Kapil Kumar | 0 | None (employee record) | Single name only - add surname | Sonia (BA)
EMP-0068 |  | Employee | Prashant Nabaghan | Sr. PM | Product | 3 | EMP-0060 | Kapil Kumar | 1 | Manager |  | Prashant Nabaghan (Sr. PM)
EMP-0069 |  | Employee | Aashish Rohhidas | BA | Product | 4 | EMP-0068 | Prashant Nabaghan | 0 | None (employee record) |  | Aashish Rohhidas (BA)
EMP-0070 |  | Employee | Parvinder Singh Chopra | Solution Architect | Product | 2 | POS-0001 | Managing Director | 4 | Manager |  | Parvinder Singh Chopra (Solution Architech)
EMP-0071 |  | Employee | Gurpreet Singh | Project Lead | Product | 3 | EMP-0070 | Parvinder Singh Chopra | 0 | None (employee record) | Name shared with another record - confirm identity | Gurpreet Singh (Project Lead)
EMP-0072 |  | Employee | Chhatarshal Singh | Team Lead Developer | Product | 3 | EMP-0070 | Parvinder Singh Chopra | 6 | Team Lead |  | Chhatarshal Singh (Team Lead Developer)
EMP-0073 |  | Employee | Kamal Kumar | Software Engineer | Product | 4 | EMP-0072 | Chhatarshal Singh | 0 | None (employee record) |  | Kamal Kumar (Software Engineer)
EMP-0074 |  | Employee | Preeti Thakur | Software Engineer | Product | 4 | EMP-0072 | Chhatarshal Singh | 0 | None (employee record) |  | Preeti Thakur (Software Engineer)
EMP-0075 |  | Employee | Rohit Chauhan | Software Engineer | Product | 4 | EMP-0072 | Chhatarshal Singh | 0 | None (employee record) |  | Rohit Chauhan (Software Engineer)
EMP-0076 |  | Employee | Savita | Software Engineer | Product | 4 | EMP-0072 | Chhatarshal Singh | 0 | None (employee record) | Single name only - add surname | Savita (Software Engineer)
EMP-0077 |  | Employee | Puneet Sharma | Software Engineer | Product | 4 | EMP-0072 | Chhatarshal Singh | 0 | None (employee record) |  | Puneet Sharma (Software Engineer)
EMP-0078 |  | Employee | Rupanshi Bhandari | Software Engineer | Product | 4 | EMP-0072 | Chhatarshal Singh | 0 | None (employee record) | Chart text malformed (fixed) | Rupanshi Bhandari ((Software Engineer)
EMP-0079 |  | Employee | Mukesh Kumar | Dev Ops Engineer | Product | 3 | EMP-0070 | Parvinder Singh Chopra | 0 | None (employee record) | Name shared with another record - confirm identity | Mukesh Kumar (Dev Ops Engineer)
EMP-0080 |  | Employee | Jyoti | Sr. Devops | Product | 3 | EMP-0070 | Parvinder Singh Chopra | 0 | None (employee record) | Single name only - add surname | Jyoti (Sr. Devops)
EMP-0081 |  | Employee | Pradeep Thakur | Lead UI/UX Designer | Product | 2 | POS-0001 | Managing Director | 3 | Team Lead |  | Pradeep Thakur (Lead UI/UX Designer)
EMP-0082 |  | Employee | Sachin Barnwal | UI/UX Designer | Product | 3 | EMP-0081 | Pradeep Thakur | 0 | None (employee record) |  | Sachin Barnwal (UI/UX Designer)
EMP-0083 |  | Employee | Maninder Singh | Sr. UI/UX Designer | Product | 3 | EMP-0081 | Pradeep Thakur | 0 | None (employee record) | Name shared with another record - confirm identity | Maninder Singh (Sr. UI/UX Designer)
EMP-0084 |  | Employee | Harsh | UI/UX Designer | Product | 3 | EMP-0081 | Pradeep Thakur | 0 | None (employee record) | Single name only - add surname | Harsh (UI/UX Designer)
EMP-0085 |  | Employee | Balneet Birah | VP-HR | HR | 1 |  |  | 2 | HOD |  | Balneet Birah (VP-HR)
EMP-0086 |  | Employee | Rakesh Guleria | AVP-HR | HR | 2 | EMP-0085 | Balneet Birah | 7 | Manager |  | Rakesh Guleria (AVP-HR)
EMP-0087 |  | Employee | Hidayat Khan | AM - HR OPS | HR | 3 | EMP-0086 | Rakesh Guleria | 1 | Manager |  | Hidayat Khan (AM - HR OPS)
POS-0088 |  | Vacant Position | (vacant) | Vacant position (empty box in chart) | HR | 4 | EMP-0087 | Hidayat Khan | 0 | None (vacant) | Vacant / unnamed position
EMP-0089 |  | Employee | Parul | CSR Manager | HR | 3 | EMP-0086 | Rakesh Guleria | 0 | None (employee record) | Single name only - add surname | Parul (CSR Manager)
EMP-0090 |  | Employee | Robin Sharma | TL OPS | HR | 3 | EMP-0086 | Rakesh Guleria | 0 | None (employee record) |  | Robin Sharma (TL OPS)
EMP-0091 |  | Employee | Amrit Kaur | Team Lead | HR | 3 | EMP-0086 | Rakesh Guleria | 0 | None (employee record) |  | Amrit Kaur (Team Lead)
EMP-0092 |  | Employee | Prabhleen Kaur | Sr. TA | HR | 3 | EMP-0086 | Rakesh Guleria | 0 | None (employee record) |  | Prabhleen Kaur (Sr. TA)
EMP-0093 |  | Employee | Himani Sharma | AM-TA | HR | 3 | EMP-0086 | Rakesh Guleria | 1 | Manager |  | Himani Sharma (AM-TA)
EMP-0094 |  | Employee | Jitender Thakur | TA | HR | 4 | EMP-0093 | Himani Sharma | 0 | None (employee record) | Name shared with another record - confirm identity | Jitender Thakur (TA)
EMP-0095 |  | Employee | Nidhi Zulka | HR Manager:MB | HR | 3 | EMP-0086 | Rakesh Guleria | 0 | None (employee record) |  | Nidhi Zulka (HR Manager:MB)
EMP-0096 |  | Employee | Deepjot Tiwari | Manager L&D | HR | 2 | EMP-0085 | Balneet Birah | 1 | Manager |  | Deepjot Tiwari ( Manager L&D)
EMP-0097 |  | Employee | Aman Thapa | Executive L&D | HR | 3 | EMP-0096 | Deepjot Tiwari | 0 | None (employee record) |  | Aman Thapa ( Executive L&D)
EMP-0098 |  | Employee | Aunj Ohri | VP Accounts | Accounts | 1 |  |  | 2 | HOD |  | Aunj Ohri (VP Accounts)
EMP-0099 |  | Employee | Pushpinder Singh | AVP - Accounts | Accounts | 2 | EMP-0098 | Aunj Ohri | 5 | Manager |  | Pushpinder Singh (AVP - Accounts)
EMP-0100 |  | Employee | Ravi Kumar | AM- Accounts | Accounts | 3 | EMP-0099 | Pushpinder Singh | 3 | Manager |  | Ravi Kumar (AM- Accounts)
EMP-0101 |  | Employee | Sarthak Sharma | Accounts Executive | Accounts | 4 | EMP-0100 | Ravi Kumar | 0 | None (employee record) |  | Sarthak Sharma (Accounts Executive)
EMP-0102 |  | Employee | Aditya Jindal | Accounts Executive | Accounts | 4 | EMP-0100 | Ravi Kumar | 0 | None (employee record) |  | Aditya Jindal (Accounts Executive)
EMP-0103 |  | Employee | Rohit Kumar | Sr. Accounts Executive | Accounts | 4 | EMP-0100 | Ravi Kumar | 0 | None (employee record) |  | Rohit Kumar (Sr. Accounts Executive)
EMP-0104 |  | Employee | Ravesh Sharma | AM - Accounts | Accounts | 3 | EMP-0099 | Pushpinder Singh | 0 | None (employee record) |  | Ravesh Sharma (AM - Accounts)
EMP-0105 |  | Employee | Bharat Maan | Sr. Accounts Executive | Accounts | 3 | EMP-0099 | Pushpinder Singh | 0 | None (employee record) |  | Bharat Maan (Sr. Accounts Executive)
EMP-0106 |  | Employee | Yadwinder Singh | Sr. Manager | Accounts | 3 | EMP-0099 | Pushpinder Singh | 0 | None (employee record) |  | Yadwinder Singh (Sr. Manager)
EMP-0107 |  | Employee | Vinod Kumar | Manager | Accounts | 3 | EMP-0099 | Pushpinder Singh | 0 | None (employee record) |  | Vinod Kumar (Manager)
EMP-0108 |  | Employee | Deepak Khanna | Accounts Manager | Accounts | 2 | EMP-0098 | Aunj Ohri | 0 | None (employee record) |  | Deepak Khanna (Accounts Manager)
EMP-0109 |  | Employee | Pawan Kumar | AVP-Operations | Demat | 1 |  |  | 6 | HOD | Name shared with another record - confirm identity; Heads multiple departments | Pawan Kumar (AVP-Operations)
EMP-0110 |  | Employee | Yogesh | DP Manager | Demat | 2 | EMP-0109 | Pawan Kumar | 6 | Manager | Single name only - add surname | Yogesh (DP Manager)
EMP-0111 |  | Employee | Swati Vashist | DP Executive | Demat | 3 | EMP-0110 | Yogesh | 0 | None (employee record) |  | Swati Vashist (DP Executive)
EMP-0112 |  | Employee | Atul Kumar | Sr. Team Lead | Demat | 3 | EMP-0110 | Yogesh | 0 | None (employee record) |  | Atul Kumar (Sr. Team Lead)
EMP-0113 |  | Employee | Rahul Bharti | DP Executive | Demat | 3 | EMP-0110 | Yogesh | 0 | None (employee record) |  | Rahul Bharti (DP Exceutive)
EMP-0114 |  | Employee | Prince Masih | Sr. Executive | Demat | 3 | EMP-0110 | Yogesh | 0 | None (employee record) |  | Prince Masih (Sr. Executive)
EMP-0115 |  | Employee | Dinesh Kumar | DP Executive | Demat | 3 | EMP-0110 | Yogesh | 0 | None (employee record) |  | Dinesh Kumar (DP Executive)
EMP-0116 |  | Employee | Rohit Dhiman | DP Executive | Demat | 3 | EMP-0110 | Yogesh | 0 | None (employee record) |  | Rohit Dhiman (DP Executive)
EMP-0117 |  | Employee | Ramneek | Head - Digital Marketing (designation not in chart) | Digital Marketing | 1 |  |  | 5 | HOD | Single name only - add surname; Designation missing | Ramneek Mam
EMP-0118 |  | Employee | Naveen Kumar | Assistant Manager | Digital Marketing | 2 | EMP-0117 | Ramneek | 6 | Manager | Name shared with another record - confirm identity | Naveen Kumar (Assistant Manager)
EMP-0119 |  | Employee | Pallavi Chauhan | Sr. SEO Executive | Digital Marketing | 3 | EMP-0118 | Naveen Kumar | 0 | None (employee record) |  | Pallavi Chauhan (Sr. SEO Executive)
EMP-0120 |  | Employee | Maninder Singh | SEO Executive | Digital Marketing | 3 | EMP-0118 | Naveen Kumar | 0 | None (employee record) | Name shared with another record - confirm identity | Maninder Singh (SEO Executive)
EMP-0121 |  | Employee | Mandeep Singh | SEO Executive | Digital Marketing | 3 | EMP-0118 | Naveen Kumar | 0 | None (employee record) |  | Mandeep Singh (SEO Executive)
EMP-0122 |  | Employee | Kunal Puri | SEO Executive | Digital Marketing | 3 | EMP-0118 | Naveen Kumar | 0 | None (employee record) |  | Kunal Puri (SEO Executive)
EMP-0123 |  | Employee | Atul Rana | SEO Executive | Digital Marketing | 3 | EMP-0118 | Naveen Kumar | 0 | None (employee record) |  | Atul Rana (SEO Executive)
EMP-0124 |  | Employee | Rohan Rawat | Sr. DM Executive | Digital Marketing | 3 | EMP-0118 | Naveen Kumar | 0 | None (employee record) |  | Rohan Rawat (Sr. DM Executive)
EMP-0125 |  | Employee | Basant Dhawan | Sr. VP-Brand Management and Marketing | Digital Marketing | 2 | EMP-0117 | Ramneek | 5 | Manager |  | Basant Dhawan (Sr. VP -Brand Management and Marketing)
EMP-0126 |  | Employee | Deesha Seth | AVP: Content Strategist | Digital Marketing | 3 | EMP-0125 | Basant Dhawan | 5 | Manager |  | Deesha Seth (AVP: Content Strategist)
EMP-0127 |  | Employee | Neel Hemang Shah | Copy Writer | Digital Marketing | 4 | EMP-0126 | Deesha Seth | 0 | None (employee record) |  | Neel Hemang Shah (Copy Writer)
EMP-0128 |  | Employee | Sampras D'souza | Sr. Copy Writer | Digital Marketing | 4 | EMP-0126 | Deesha Seth | 0 | None (employee record) |  | Sampras D'souza (Sr. Copy Writer)
EMP-0129 |  | Employee | Parag Sonone | Sr. Copywriter | Digital Marketing | 4 | EMP-0126 | Deesha Seth | 0 | None (employee record) |  | Parag Sonone (Sr. Copywriter)
EMP-0130 |  | Employee | Ananya Walia | Content Writer | Digital Marketing | 4 | EMP-0126 | Deesha Seth | 0 | None (employee record) |  | Ananya Walia (Content Writer)
EMP-0131 |  | Employee | Gurnoor Saini | Sr. Content Writer | Digital Marketing | 4 | EMP-0126 | Deesha Seth | 0 | None (employee record) |  | Gurnoor Saini (Sr. Content Writer)
EMP-0132 |  | Employee | Smeet Paresh Shah | Sr. Manager-Graphics | Digital Marketing | 3 | EMP-0125 | Basant Dhawan | 4 | Manager |  | Smeet Paresh Shah (Sr. Manager-Graphics)
EMP-0133 |  | Employee | Atul Narendra Sharma | Graphic and Video Editor | Digital Marketing | 4 | EMP-0132 | Smeet Paresh Shah | 0 | None (employee record) |  | Atul Narendra Sharma (Graphic and Video Editor)
EMP-0134 |  | Employee | Vishal Kumar | Lead Video Production | Digital Marketing | 4 | EMP-0132 | Smeet Paresh Shah | 0 | None (employee record) |  | Vishal Kumar (Lead Video Production)
EMP-0135 |  | Employee | Harsh Bhatia | Graphic Designer | Digital Marketing | 4 | EMP-0132 | Smeet Paresh Shah | 0 | None (employee record) |  | Harsh Bhatia (Graphic Designer)
EMP-0136 |  | Employee | Atish Kumar | Sr. UI/UX Designer | Digital Marketing | 4 | EMP-0132 | Smeet Paresh Shah | 0 | None (employee record) |  | Atish Kumar (Sr. UI/UX Designer)
EMP-0137 |  | Employee | Ishaque Gulam | AVP: ORM | Digital Marketing | 3 | EMP-0125 | Basant Dhawan | 3 | Manager |  | Ishaque Gulam (AVP: ORM)
EMP-0138 |  | Employee | Rohit Rajendra Bhosale | Campaign Manager | Digital Marketing | 4 | EMP-0137 | Ishaque Gulam | 1 | Manager |  | Rohit Rajendra Bhosale (Campaign Manager)
EMP-0139 |  | Employee | Kusum Khimraj Kumavat | Marketing Associate | Digital Marketing | 5 | EMP-0138 | Rohit Rajendra Bhosale | 0 | None (employee record) |  | Kusum Khimraj Kumavat (Marketing Associate)
EMP-0140 |  | Employee | Manisha Saxena | Team Lead | Digital Marketing | 4 | EMP-0137 | Ishaque Gulam | 3 | Team Lead |  | Manisha Saxena (Team Lead)
EMP-0141 |  | Employee | Richa Sharma | Executive | Digital Marketing | 5 | EMP-0140 | Manisha Saxena | 0 | None (employee record) |  | Richa Sharma (Executive)
EMP-0142 |  | Employee | Minakshi | Executive | Digital Marketing | 5 | EMP-0140 | Manisha Saxena | 0 | None (employee record) | Single name only - add surname | Minakshi (Executive)
EMP-0143 |  | Employee | Shruti Sharma | Executive | Digital Marketing | 5 | EMP-0140 | Manisha Saxena | 0 | None (employee record) |  | Shruti Sharma (Executive)
EMP-0144 |  | Employee | Divyanshi Aggarwal | AM | Digital Marketing | 4 | EMP-0137 | Ishaque Gulam | 2 | Manager |  | Divyanshi Aggarwal (AM)
EMP-0145 |  | Employee | Shoa Fatima | Executive | Digital Marketing | 5 | EMP-0144 | Divyanshi Aggarwal | 0 | None (employee record) |  | Shoa Fatima (Executive)
EMP-0146 |  | Employee | Ananya Sharma | Executive | Digital Marketing | 5 | EMP-0144 | Divyanshi Aggarwal | 0 | None (employee record) |  | Ananya Sharma (Executive)
EMP-0147 |  | Employee | Sonal Mulye | AVP | Digital Marketing | 3 | EMP-0125 | Basant Dhawan | 5 | Manager |  | Sonal Mulye (AVP)
EMP-0148 |  | Employee | Kamlesh Jain | Tech. Research Analyst | Digital Marketing | 4 | EMP-0147 | Sonal Mulye | 0 | None (employee record) |  | Kamlesh Jain (Tech. Research Analyst)
EMP-0149 |  | Employee | Deep Himanshu | Tech. Research Analyst | Digital Marketing | 4 | EMP-0147 | Sonal Mulye | 0 | None (employee record) |  | Deep Himanshu (Tech. Research Analyst)
EMP-0150 |  | Employee | Abhishay Rajeev Upasham | Equity Research Analyst | Digital Marketing | 4 | EMP-0147 | Sonal Mulye | 0 | None (employee record) |  | ABHISHAY RAJEEV UPASHAM (Equity Research Analyst)
EMP-0151 |  | Employee | Shubhanshi Satish Dixit | Sr. DM Executive | Digital Marketing | 4 | EMP-0147 | Sonal Mulye | 0 | None (employee record) |  | Shubhanshi Satish Dixit (Sr. DM Executive)
EMP-0152 |  | Employee | Aastha Johri | Sr. Executive | Digital Marketing | 4 | EMP-0147 | Sonal Mulye | 0 | None (employee record) | Chart text malformed (fixed) | Aastha Johri (Sr. Executive
EMP-0153 |  | Employee | Miteeksha | Manager - Content | Digital Marketing | 3 | EMP-0125 | Basant Dhawan | 0 | None (employee record) | Single name only - add surname; Chart text malformed (fixed) | Miteeksha (Manager - Content
EMP-0154 |  | Employee | Sonali Karamchandni | Influencer Marketing Manager | Digital Marketing | 2 | EMP-0117 | Ramneek | 0 | None (employee record) |  | Sonali Karamchandni (Influencer Marketing Manager)
EMP-0155 |  | Employee | Rajesh Kumar | Sr. SEO Specialist | Digital Marketing | 2 | EMP-0117 | Ramneek | 0 | None (employee record) | Name shared with another record - confirm identity | Rajesh Kumar (Sr. SEO Specialist)
EMP-0156 |  | Employee | Vaishalika Nair | Sr. SEO Specialist | Digital Marketing | 2 | EMP-0117 | Ramneek | 0 | None (employee record) |  | Vaishalika Nair(Sr. SEO Specialist)
EMP-0157 |  | Employee | Patel Rajesh | VP - IT | IT | 1 |  |  | 4 | HOD |  | Patel Rajesh (VP - IT)
EMP-0158 |  | Employee | Gaurav Pandav | AM: IT | IT | 2 | EMP-0157 | Patel Rajesh | 0 | None (employee record) |  | Gaurav Pandav (AM: IT)
EMP-0159 |  | Employee | Abhinav Wani | Sr. AWS Engineer | IT | 2 | EMP-0157 | Patel Rajesh | 0 | None (employee record) |  | Abhinav Wani (Sr. AWS Engineer)
EMP-0160 |  | Employee | Kartik Vembukumar | Sr. IT | IT | 2 | EMP-0157 | Patel Rajesh | 0 | None (employee record) |  | Kartik Vembukumar (Sr. IT)
EMP-0161 |  | Employee | Gurpreet Singh | Manager | IT | 2 | EMP-0157 | Patel Rajesh | 4 | Manager | Name shared with another record - confirm identity | Gurpreet Singh (Manager)
EMP-0162 |  | Employee | Sourav Kumar | Team Lead: IT | IT | 3 | EMP-0161 | Gurpreet Singh | 2 | Team Lead |  | Sourav Kumar (Team Lead: IT)
EMP-0163 |  | Employee | Neeraj Kumar | IT Executive | IT | 4 | EMP-0162 | Sourav Kumar | 0 | None (employee record) | Name shared with another record - confirm identity | Neeraj Kumar (IT Executive)
EMP-0164 |  | Employee | Himanshu | Executive: IT Monitoring & Support | IT | 4 | EMP-0162 | Sourav Kumar | 0 | None (employee record) | Single name only - add surname | Himanshu (Executive: IT Monitoring & Support)
EMP-0165 |  | Employee | Sunil Kumar | Network Administrator | IT | 3 | EMP-0161 | Gurpreet Singh | 1 | Manager |  | Sunil Kumar (Network Administrator)
EMP-0166 |  | Employee | Bhuvneshwar | Server Administrator | IT | 4 | EMP-0165 | Sunil Kumar | 0 | None (employee record) | Single name only - add surname | Bhuvneshwar (Server Administrator)
EMP-0167 |  | Employee | Munish Kumar | Executive:IT | IT | 3 | EMP-0161 | Gurpreet Singh | 0 | None (employee record) |  | Munish Kumar (Exeutive:IT)
EMP-0168 |  | Employee | Sahibpreet Singh | Executive:IT | IT | 3 | EMP-0161 | Gurpreet Singh | 0 | None (employee record) |  | Sahibpreet Singh (Executive:IT)
EMP-0109 |  | Employee | Pawan Kumar | AVP-Operations | Operations & BO | 1 |  |  | 6 | HOD | Name shared with another record - confirm identity; Heads multiple departments | Pawan (AVP - Operations)
EMP-0169 |  | Employee | Sanjay Kaushik | Team Lead | Operations & BO | 2 | EMP-0109 | Pawan Kumar | 4 | Team Lead |  | Sanjay Kaushik (Team Lead)
EMP-0170 |  | Employee | Vinay Thakur | Ops Executive | Operations & BO | 3 | EMP-0169 | Sanjay Kaushik | 0 | None (employee record) |  | Vinay Thakur (Ops. Executive)
EMP-0171 |  | Employee | Sukhpal Singh | Ops Executive | Operations & BO | 3 | EMP-0169 | Sanjay Kaushik | 0 | None (employee record) |  | Sukhpal Singh (Ops. Executive)
EMP-0172 |  | Employee | Manish Sharma | Ops Executive | Operations & BO | 3 | EMP-0169 | Sanjay Kaushik | 0 | None (employee record) |  | Manish Sharma ( OPs. Executive)
EMP-0173 |  | Employee | Abhishek | Ops Executive | Operations & BO | 3 | EMP-0169 | Sanjay Kaushik | 0 | None (employee record) | Single name only - add surname | Abhishek (OPs. Executive)
EMP-0174 |  | Employee | Vivek Sharma | Sr. BO Manager | Operations & BO | 2 | EMP-0109 | Pawan Kumar | 4 | Manager |  | Vivek Sharma (Sr. BO Manager)
EMP-0175 |  | Employee | Kanav Verma | Team Lead | Operations & BO | 3 | EMP-0174 | Vivek Sharma | 5 | Team Lead |  | Kanav Verma (Team Lead)
EMP-0176 |  | Employee | Ashwani | Sr. BO Executive | Operations & BO | 4 | EMP-0175 | Kanav Verma | 0 | None (employee record) | Single name only - add surname | Ashwani (Sr. BO Executive)
EMP-0177 |  | Employee | Lakhbir Singh | BO Executive | Operations & BO | 4 | EMP-0175 | Kanav Verma | 0 | None (employee record) |  | Lakhbir Singh (BO Executive)
EMP-0178 |  | Employee | Tarnum | BO Executive | Operations & BO | 4 | EMP-0175 | Kanav Verma | 0 | None (employee record) | Single name only - add surname | Tarnum (BO Executive)
EMP-0179 |  | Employee | Jitender Thakur | BO Executive | Operations & BO | 4 | EMP-0175 | Kanav Verma | 0 | None (employee record) | Name shared with another record - confirm identity | Jitender Thakur (BO Executive)
EMP-0180 |  | Employee | Anil Kumar | BO Executive | Operations & BO | 4 | EMP-0175 | Kanav Verma | 0 | None (employee record) |  | ANIL KUMAR (BO Executive)
EMP-0181 |  | Employee | Jai Dev Singh | Team Lead | Operations & BO | 3 | EMP-0174 | Vivek Sharma | 5 | Team Lead |  | Jai Dev Singh (Team Lead)
EMP-0182 |  | Employee | Devinder Singh | BO Executive | Operations & BO | 4 | EMP-0181 | Jai Dev Singh | 0 | None (employee record) |  | Devinder Singh (BO Executive)
EMP-0183 |  | Employee | Anmol Koundal | BO Executive | Operations & BO | 4 | EMP-0181 | Jai Dev Singh | 0 | None (employee record) |  | Anmol Koundal (BO Executive)
EMP-0184 |  | Employee | Palak Mahajan | BO Executive | Operations & BO | 4 | EMP-0181 | Jai Dev Singh | 0 | None (employee record) |  | Palak Mahajan (BO Executive)
EMP-0185 |  | Employee | Neeraj | BO Executive | Operations & BO | 4 | EMP-0181 | Jai Dev Singh | 0 | None (employee record) | Single name only - add surname | Neeraj(BO Executive)
EMP-0186 |  | Employee | Kalpana | Sr. BO Executive | Operations & BO | 4 | EMP-0181 | Jai Dev Singh | 0 | None (employee record) | Single name only - add surname | Kalpana (Sr. BO Executive)
EMP-0187 |  | Employee | Akashdeep | Team Lead | Operations & BO | 3 | EMP-0174 | Vivek Sharma | 5 | Team Lead | Single name only - add surname | Akashdeep (Team Lead)
EMP-0188 |  | Employee | Pragna | BO Executive | Operations & BO | 4 | EMP-0187 | Akashdeep | 0 | None (employee record) | Single name only - add surname | Pragna (BO Executive)
EMP-0189 |  | Employee | Sumish | BO Executive | Operations & BO | 4 | EMP-0187 | Akashdeep | 0 | None (employee record) | Single name only - add surname | Sumish (BO Executive)
EMP-0190 |  | Employee | Sonam | BO Executive | Operations & BO | 4 | EMP-0187 | Akashdeep | 0 | None (employee record) | Single name only - add surname | Sonam (BO Executive)
EMP-0191 |  | Employee | Deepak Kumar | BO Executive | Operations & BO | 4 | EMP-0187 | Akashdeep | 0 | None (employee record) | Chart text malformed (fixed) | DEEPAK KUMAR (BO Executive
EMP-0192 |  | Employee | Akshit Sandal | BO Executive | Operations & BO | 4 | EMP-0187 | Akashdeep | 0 | None (employee record) |  | AKSHIT SANDAL (BO Executive)
EMP-0193 |  | Employee | Yachika | Team Lead | Operations & BO | 3 | EMP-0174 | Vivek Sharma | 1 | Team Lead | Single name only - add surname | Yachika (Team Lead)
EMP-0194 |  | Employee | Suman | Sr. BO Executive | Operations & BO | 4 | EMP-0193 | Yachika | 0 | None (employee record) | Single name only - add surname | Suman (Sr. BO Executive)
EMP-0195 |  | Employee | Parvinder Kaur | Team Lead:Surveillance | Operations & BO | 2 | EMP-0109 | Pawan Kumar | 1 | Team Lead |  | Parvinder Kaur (Team Lead:Survelliance)
EMP-0196 |  | Employee | Anuj Patial | BO Executive | Operations & BO | 3 | EMP-0195 | Parvinder Kaur | 0 | None (employee record) |  | Anuj Patial (BO Executive)
EMP-0109 |  | Employee | Pawan Kumar | AVP-Operations | Compliance | 1 |  |  | 6 | HOD | Name shared with another record - confirm identity; Heads multiple departments | Pawan Kumar (AVP-Operations)
EMP-0197 |  | Employee | Akanksha Chhabra | Manager Compliance | Compliance | 2 | EMP-0109 | Pawan Kumar | 3 | Manager |  | Akanksha Chhabra ( Manager Compliance)
EMP-0198 |  | Employee | Hardeep Singh | AM Compliance | Compliance | 3 | EMP-0197 | Akanksha Chhabra | 0 | None (employee record) | Name shared with another record - confirm identity | Hardeep Singh (AM Compliance)
EMP-0199 |  | Employee | Kartik Khatwal | Executive Compliance | Compliance | 3 | EMP-0197 | Akanksha Chhabra | 0 | None (employee record) |  | Kartik Khatwal (Executive Compliance)
POS-0200 |  | Vacant Position | (vacant) | AM Compliance | Compliance | 3 | EMP-0197 | Akanksha Chhabra | 0 | None (vacant) | Vacant / unnamed position | AM Compliance
EMP-0201 |  | Employee | Kunal Malviya | Manager Compliance | Compliance | 2 | EMP-0109 | Pawan Kumar | 1 | Manager |  | Kunal Malviya ( Manager Compliance)
EMP-0202 |  | Employee | Mohd. Ali Khan | Sr Executive | Compliance | 3 | EMP-0201 | Kunal Malviya | 0 | None (employee record) |  | Mohd. Ali Khan ( Sr Executive)
EMP-0203 |  | Employee | Ayushman Dey | Sr. RMS Manager | RMS & Dealer | 1 |  |  | 6 | HOD |  | Ayushman Dey (Sr. RMS Manager)
EMP-0204 |  | Employee | Naveen Kumar | RMS Manager | RMS & Dealer | 2 | EMP-0203 | Ayushman Dey | 4 | Manager | Name shared with another record - confirm identity | Naveen Kumar (RMS Manager)
EMP-0205 |  | Employee | Neeraj Kumar | Sr. RMS Executive | RMS & Dealer | 3 | EMP-0204 | Naveen Kumar | 0 | None (employee record) | Name shared with another record - confirm identity | Neeraj Kumar (Sr. RMS Executive)
EMP-0206 |  | Employee | Salim Khan | RMS Executive | RMS & Dealer | 3 | EMP-0204 | Naveen Kumar | 0 | None (employee record) | Name shared with another record - confirm identity; Appears twice in same chart - possible duplicate | Salim Khan (RMS Executive)
EMP-0207 |  | Employee | Vineet Thakur | Lead RMS | RMS & Dealer | 3 | EMP-0204 | Naveen Kumar | 0 | None (employee record) |  | Vineet Thakur (Lead RMS)
EMP-0208 |  | Employee | Salim Khan | RMS Executive | RMS & Dealer | 3 | EMP-0204 | Naveen Kumar | 0 | None (employee record) | Name shared with another record - confirm identity; Appears twice in same chart - possible duplicate | Salim Khan (RMS Executive)
EMP-0209 |  | Employee | Anil Kumar Dubey | Manager | RMS & Dealer | 2 | EMP-0203 | Ayushman Dey | 0 | None (employee record) |  | Anil Kumar Dubey (Manager)
EMP-0210 |  | Employee | Chetan Chandrakant | AM | RMS & Dealer | 2 | EMP-0203 | Ayushman Dey | 0 | None (employee record) |  | Chetan Chandrakant (AM)
EMP-0211 |  | Employee | Kuldeep Kumar | Dealer Manager | RMS & Dealer | 2 | EMP-0203 | Ayushman Dey | 2 | Manager |  | Kuldeep Kumar (Dealer Manager)
EMP-0212 |  | Employee | Jagat Singh | Sr. Dealer | RMS & Dealer | 3 | EMP-0211 | Kuldeep Kumar | 0 | None (employee record) |  | Jagat Singh (Sr. Dealer)
EMP-0213 |  | Employee | Lakhan Singh | Sr. Dealer | RMS & Dealer | 3 | EMP-0211 | Kuldeep Kumar | 0 | None (employee record) |  | Lakhan Singh (Sr. Dealer)
EMP-0214 |  | Employee | Ajay Rana | Dealer Manager | RMS & Dealer | 2 | EMP-0203 | Ayushman Dey | 3 | Manager |  | Ajay Rana (Dealer Manager)
EMP-0215 |  | Employee | Sher Singh | Sr. Dealer | RMS & Dealer | 3 | EMP-0214 | Ajay Rana | 0 | None (employee record) |  | Sher Singh (Sr. Dealer)
EMP-0216 |  | Employee | Vikram Singh Thakur | Sr. Dealer | RMS & Dealer | 3 | EMP-0214 | Ajay Rana | 0 | None (employee record) |  | Vikram Singh Thakur (Sr. Dealer)
EMP-0217 |  | Employee | Nishant Kumar | Sr. Dealer | RMS & Dealer | 3 | EMP-0214 | Ajay Rana | 0 | None (employee record) |  | Nishant Kumar (Sr. Dealer)
EMP-0218 |  | Employee | Samrudhhi Sandeep Jadhav | AM- RMS | RMS & Dealer | 2 | EMP-0203 | Ayushman Dey | 0 | None (employee record) |  | SAMRUDHHI SANDEEP JADHAV (AM- RMS)
EMP-0219 |  | Employee | Kapil Abrol | AVP-CS | Client Support | 1 |  |  | 1 | HOD |  | Kapil Abrol (AVP -CS)
EMP-0220 |  | Employee | Angel Sharma | Sr. Manager | Client Support | 2 | EMP-0219 | Kapil Abrol | 7 | Manager |  | Angel Sharma (Sr. Manager)
EMP-0221 |  | Employee | Sahil Sharma | AM-CS | Client Support | 3 | EMP-0220 | Angel Sharma | 3 | Manager |  | Sahil Sharma (AM-CS)
EMP-0222 |  | Employee | Ramandeep Kaur | Sr. CS Executive | Client Support | 4 | EMP-0221 | Sahil Sharma | 1 | Manager | Name shared with another record - confirm identity; Chart text malformed (fixed) | Ramandeep Kaur (Sr. CS Executive
EMP-0223 |  | Employee | Ankit | CS Executive | Client Support | 5 | EMP-0222 | Ramandeep Kaur | 0 | None (employee record) | Name shared with another record - confirm identity; Single name only - add surname | Ankit (CS Executive)
EMP-0224 |  | Employee | Aaina Ghill | Team Lead | Client Support | 4 | EMP-0221 | Sahil Sharma | 5 | Team Lead |  | Aaina Ghill (Team Lead)
EMP-0225 |  | Employee | Arun | Sr. CS Executive | Client Support | 5 | EMP-0224 | Aaina Ghill | 0 | None (employee record) | Single name only - add surname | Arun (Sr. CS Executive)
EMP-0226 |  | Employee | Kiritika Kanwar | CS Executive | Client Support | 5 | EMP-0224 | Aaina Ghill | 0 | None (employee record) |  | Kiritika Kanwar (CS Executive)
EMP-0227 |  | Employee | Shalini Dhiman | CS Executive | Client Support | 5 | EMP-0224 | Aaina Ghill | 0 | None (employee record) |  | Shalini Dhiman (CS Executive)
EMP-0228 |  | Employee | Sachin | CS Executive | Client Support | 5 | EMP-0224 | Aaina Ghill | 0 | None (employee record) | Single name only - add surname | Sachin (CS Executive)
EMP-0229 |  | Employee | Shagun | CS Executive | Client Support | 5 | EMP-0224 | Aaina Ghill | 0 | None (employee record) | Single name only - add surname | Shagun (CS Executive)
EMP-0230 |  | Employee | Jaspal | Team Lead | Client Support | 4 | EMP-0221 | Sahil Sharma | 4 | Team Lead | Single name only - add surname | Jaspal (Team Lead)
EMP-0231 |  | Employee | Siya Bhadwal | CS Executive | Client Support | 5 | EMP-0230 | Jaspal | 0 | None (employee record) |  | Siya Bhadwal (CS Executive)
EMP-0232 |  | Employee | Harsh Kumar | CS Executive | Client Support | 5 | EMP-0230 | Jaspal | 0 | None (employee record) |  | Harsh Kumar (CS Executive)
EMP-0233 |  | Employee | Akriti | Sr. CS Executive | Client Support | 5 | EMP-0230 | Jaspal | 2 | Manager | Single name only - add surname | Akriti (Sr. CS Executive)
EMP-0234 |  | Employee | Anuj Kumar | CS Executive | Client Support | 6 | EMP-0233 | Akriti | 0 | None (employee record) |  | Anuj Kumar (CS Executive)
EMP-0235 |  | Employee | Rajdeep Kaur | CS Executive | Client Support | 6 | EMP-0233 | Akriti | 0 | None (employee record) |  | Rajdeep Kaur (CS Executive)
EMP-0236 |  | Employee | Kajal | CS Executive | Client Support | 5 | EMP-0230 | Jaspal | 0 | None (employee record) | Single name only - add surname | Kajal (CS Executive)
EMP-0237 |  | Employee | Adity Chiba | Sr. CS Manager | Client Support | 3 | EMP-0220 | Angel Sharma | 3 | Manager |  | Adity Chiba (Sr. .CS Manager)
EMP-0238 |  | Employee | Savita Rawat | CS Executive | Client Support | 4 | EMP-0237 | Adity Chiba | 0 | None (employee record) |  | Savita Rawat (CS Executive)
EMP-0239 |  | Employee | Neeru Arya | Sr. Team Lead | Client Support | 4 | EMP-0237 | Adity Chiba | 6 | Team Lead |  | Neeru Arya (Sr. Team Lead)
EMP-0240 |  | Employee | Amritpal Singh | CS Executive | Client Support | 5 | EMP-0239 | Neeru Arya | 0 | None (employee record) | Name shared with another record - confirm identity; Appears twice in same chart - possible duplicate | Amritpal Singh (CS Executive)
EMP-0241 |  | Employee | Shubham | CS Executive | Client Support | 5 | EMP-0239 | Neeru Arya | 0 | None (employee record) | Single name only - add surname | Shubham (CS Executive)
EMP-0242 |  | Employee | Kartika | Sr. CS Executive | Client Support | 5 | EMP-0239 | Neeru Arya | 0 | None (employee record) | Single name only - add surname | Kartika (Sr. CS Executive)
EMP-0243 |  | Employee | Nikhil | CS Executive | Client Support | 5 | EMP-0239 | Neeru Arya | 0 | None (employee record) | Single name only - add surname | Nikhil (CS Executive)
EMP-0244 |  | Employee | Saurabh Bhardwaj | CS Executive | Client Support | 5 | EMP-0239 | Neeru Arya | 0 | None (employee record) |  | Saurabh Bhardwaj (CS Executive)
EMP-0245 |  | Employee | Ajay Kumar | CS Executive | Client Support | 5 | EMP-0239 | Neeru Arya | 0 | None (employee record) |  | Ajay Kumar (CS Executive)
EMP-0246 |  | Employee | Vishakha Sharma | AM-CS | Client Support | 4 | EMP-0237 | Adity Chiba | 2 | Manager |  | Vishakha Sharma (AM-CS)
EMP-0247 |  | Employee | Dilpreet Kaur | CS Executive | Client Support | 5 | EMP-0246 | Vishakha Sharma | 0 | None (employee record) |  | Dilpreet Kaur (CS Executive)
EMP-0248 |  | Employee | Tarun Khajuria | CS Executive | Client Support | 5 | EMP-0246 | Vishakha Sharma | 0 | None (employee record) |  | Tarun Khajuria (CS Executive)
EMP-0249 |  | Employee | Abhimanyu Thakur | CS Executive | Client Support | 3 | EMP-0220 | Angel Sharma | 0 | None (employee record) |  | Abhimanyu Thakur (CS Executive)
EMP-0250 |  | Employee | Hardeep Singh | CS Executive | Client Support | 3 | EMP-0220 | Angel Sharma | 0 | None (employee record) | Name shared with another record - confirm identity; Chart text malformed (fixed) | Hardeep Singh (CS EXecutive
EMP-0251 |  | Employee | Kamaljeet Kaur | CS Executive | Client Support | 3 | EMP-0220 | Angel Sharma | 0 | None (employee record) | Chart text malformed (fixed) | Kamaljeet Kaur (CS Executive
EMP-0252 |  | Employee | Amritpal Singh | CS Executive | Client Support | 3 | EMP-0220 | Angel Sharma | 0 | None (employee record) | Name shared with another record - confirm identity; Appears twice in same chart - possible duplicate | Amritpal Singh (CS Executive)
EMP-0253 |  | Employee | Vidyotma Khanna | CS Executive | Client Support | 3 | EMP-0220 | Angel Sharma | 0 | None (employee record) |  | Vidyotma Khanna (CS Executive)
EMP-0254 |  | Employee | Kapil Sachdev | AVP-CS | jUMPP CS & Sales | 1 |  |  | 2 | HOD |  | Kapil Sachdev (AVP -CS)
EMP-0255 |  | Employee | Jyoti Kapoor | Manager: CS | jUMPP CS & Sales | 2 | EMP-0254 | Kapil Sachdev | 2 | Manager |  | Jyoti Kapoor (Manager: CS)
EMP-0256 |  | Employee | Priyanka Rana | Team Lead:CS | jUMPP CS & Sales | 3 | EMP-0255 | Jyoti Kapoor | 2 | Team Lead |  | Priyanka Rana (Team Lead:CS)
EMP-0257 |  | Employee | Arti | CS Executive | jUMPP CS & Sales | 4 | EMP-0256 | Priyanka Rana | 0 | None (employee record) | Single name only - add surname | Arti (CS Executive)
EMP-0258 |  | Employee | Sakshi Sharma | CS Executive | jUMPP CS & Sales | 4 | EMP-0256 | Priyanka Rana | 0 | None (employee record) | Name shared with another record - confirm identity | Sakshi Sharma (CS Executive)
EMP-0259 |  | Employee | Jaspal Kaur | CS Executive | jUMPP CS & Sales | 3 | EMP-0255 | Jyoti Kapoor | 0 | None (employee record) |  | Jaspal Kaur (CS Executive)
EMP-0260 |  | Employee | Manish Chauhan | Manager: Sales | jUMPP CS & Sales | 2 | EMP-0254 | Kapil Sachdev | 4 | Manager |  | Manish Chauhan (Manager: Sales)
EMP-0261 |  | Employee | Deepak Goswami | Team Lead:Sales | jUMPP CS & Sales | 3 | EMP-0260 | Manish Chauhan | 0 | None (employee record) |  | Deepak Goswami (Team Lead:Sales)
EMP-0262 |  | Employee | Varun Joan | Sales Executive | jUMPP CS & Sales | 3 | EMP-0260 | Manish Chauhan | 0 | None (employee record) | Chart text malformed (fixed) | Varun Joan (Sales Executive
EMP-0263 |  | Employee | Himani Kaushik | Sales Executive | jUMPP CS & Sales | 3 | EMP-0260 | Manish Chauhan | 0 | None (employee record) |  | Himani Kaushik (Sales Executive)
EMP-0264 |  | Employee | Priyanka Negi | Sales Executive | jUMPP CS & Sales | 3 | EMP-0260 | Manish Chauhan | 0 | None (employee record) | Chart text malformed (fixed) | Priyanka Negi (Sales EXecutive
EMP-0265 |  | Employee | Gurjot Singh | AVP-Sales | Sales | 1 |  |  | 7 | HOD |  | Gurjot Singh (AVP -Sales)
EMP-0266 |  | Employee | Amit Kumar | Manager | Sales | 2 | EMP-0265 | Gurjot Singh | 3 | Manager | Name shared with another record - confirm identity | Amit Kumar (Manager)
EMP-0267 |  | Employee | Parmodh Singh | Team Lead | Sales | 3 | EMP-0266 | Amit Kumar | 5 | Team Lead |  | Parmodh Singh (Team Lead)
EMP-0268 |  | Employee | Gouri | Sales Executive | Sales | 4 | EMP-0267 | Parmodh Singh | 0 | None (employee record) | Single name only - add surname | Gouri (Sales Executive)
EMP-0269 |  | Employee | Satwinder Singh | RM | Sales | 4 | EMP-0267 | Parmodh Singh | 0 | None (employee record) |  | Satwinder Singh (RM)
EMP-0270 |  | Employee | Ashwani Kumar | Sales Executive | Sales | 4 | EMP-0267 | Parmodh Singh | 0 | None (employee record) |  | Ashwani Kumar (Sales Exective)
EMP-0271 |  | Employee | Shweta Jadhav | Front Office Executive | Sales | 4 | EMP-0267 | Parmodh Singh | 0 | None (employee record) |  | Shweta Jadhav (Front Office Executive)
EMP-0272 |  | Employee | Shalini Ambavane | Sr. Sales Executive | Sales | 4 | EMP-0267 | Parmodh Singh | 0 | None (employee record) |  | Shalini Ambavane (Sr. Sales Executive)
EMP-0273 |  | Employee | Amanpreet | Team Lead | Sales | 3 | EMP-0266 | Amit Kumar | 3 | Team Lead | Single name only - add surname | Amanpreet (Team Lead)
EMP-0274 |  | Employee | Shivani | Sr. Sales Executive | Sales | 4 | EMP-0273 | Amanpreet | 0 | None (employee record) | Single name only - add surname | Shivani (Sr. Sales Executive)
EMP-0275 |  | Employee | Shivani Dhiman | Sales Executive | Sales | 4 | EMP-0273 | Amanpreet | 0 | None (employee record) |  | Shivani Dhiman (Sales Executive)
EMP-0276 |  | Employee | Salamat Ali Shah | Sr. Sales Executive | Sales | 4 | EMP-0273 | Amanpreet | 0 | None (employee record) |  | Salamat Ali Shah (Sr. Sales Executive)
EMP-0277 |  | Employee | Shubham Sharma | Team Lead | Sales | 3 | EMP-0266 | Amit Kumar | 2 | Team Lead |  | Shubham Sharma (Team Lead)
EMP-0278 |  | Employee | Anita Rajinder | Sales Executive | Sales | 4 | EMP-0277 | Shubham Sharma | 0 | None (employee record) |  | Anita Rajinder (Sales Executive)
EMP-0279 |  | Employee | Simarjit Kaur | Sales Executive | Sales | 4 | EMP-0277 | Shubham Sharma | 0 | None (employee record) |  | Simarjit Kaur(Sales Executive)
EMP-0280 |  | Employee | Rajesh Kumar | Sr. Manager | Sales | 2 | EMP-0265 | Gurjot Singh | 2 | Manager | Name shared with another record - confirm identity | Rajesh Kumar (Sr. Manager)
EMP-0281 |  | Employee | Sakshi Sharma | Team Lead | Sales | 3 | EMP-0280 | Rajesh Kumar | 5 | Team Lead | Name shared with another record - confirm identity | Sakshi Sharma (Team Lead)
EMP-0282 |  | Employee | Alishba Khan | Sales Executive | Sales | 4 | EMP-0281 | Sakshi Sharma | 0 | None (employee record) |  | Alishba Khan (Sales Executive)
EMP-0283 |  | Employee | Ramandeep Kaur | Sales Executive | Sales | 4 | EMP-0281 | Sakshi Sharma | 0 | None (employee record) | Name shared with another record - confirm identity | Ramandeep Kaur (Sales Executive)
EMP-0284 |  | Employee | Tanu Thakur | Sales Executive | Sales | 4 | EMP-0281 | Sakshi Sharma | 0 | None (employee record) |  | Tanu Thakur (Sales Executive)
EMP-0285 |  | Employee | Rajat Kapoor | Sales Executive | Sales | 4 | EMP-0281 | Sakshi Sharma | 0 | None (employee record) |  | Rajat Kapoor (Sales Executive)
EMP-0286 |  | Employee | Ujjwala Yadav | Sales Executive | Sales | 4 | EMP-0281 | Sakshi Sharma | 0 | None (employee record) |  | Ujjwala Yadav (Sales Executive)
EMP-0287 |  | Employee | Anshul Thakur | Team Lead | Sales | 3 | EMP-0280 | Rajesh Kumar | 5 | Team Lead |  | Anshul Thakur (Team Lead)
EMP-0288 |  | Employee | Upasna | Sales Executive | Sales | 4 | EMP-0287 | Anshul Thakur | 0 | None (employee record) | Single name only - add surname | Upasna (Sales Executive)
EMP-0289 |  | Employee | Babita Thakur | Sales Executive | Sales | 4 | EMP-0287 | Anshul Thakur | 0 | None (employee record) |  | Babita Thakur (Sales Executive)
EMP-0290 |  | Employee | Kulwinder Kaur | Sales Executive | Sales | 4 | EMP-0287 | Anshul Thakur | 0 | None (employee record) |  | Kulwinder Kaur (Sales Executive)
EMP-0291 |  | Employee | Rahul Joshi | Sr. Sales Executive | Sales | 4 | EMP-0287 | Anshul Thakur | 0 | None (employee record) |  | Rahul Joshi (Sr. Sales Executive)
EMP-0292 |  | Employee | Nadeem M | Sales Executive | Sales | 4 | EMP-0287 | Anshul Thakur | 0 | None (employee record) |  | Nadeem M (Sales Executive)
EMP-0293 |  | Employee | Keshav Khullar | Business Research Analyst | Sales | 2 | EMP-0265 | Gurjot Singh | 1 | Manager |  | Keshav Khullar (Businnes Research Analyst)
EMP-0294 |  | Employee | Kunal Sethi | Brand Partner Associate | Sales | 3 | EMP-0293 | Keshav Khullar | 0 | None (employee record) |  | Kunal Sethi (Brand Partner Associate)
EMP-0295 |  | Employee | Anju Kumari | Sr. Team Leader | Sales | 2 | EMP-0265 | Gurjot Singh | 2 | Manager |  | Anju Kumari (Sr. Team Leader)
EMP-0296 |  | Employee | Sunaina Joshi | Sales Executive | Sales | 3 | EMP-0295 | Anju Kumari | 0 | None (employee record) |  | Sunaina Joshi (Sales Executive)
EMP-0297 |  | Employee | Neha Solanki | Sales Executive | Sales | 3 | EMP-0295 | Anju Kumari | 0 | None (employee record) |  | Neha Solanki (Sales Executive)
EMP-0298 |  | Employee | Durga Paswan | Associate Sales Manager | Sales | 2 | EMP-0265 | Gurjot Singh | 1 | Manager |  | Durga Paswan (Associate Sales Manager)
EMP-0299 |  | Employee | Deepak Moraina | Sales Executive | Sales | 3 | EMP-0298 | Durga Paswan | 0 | None (employee record) |  | Deepak Moraina (Sales Executive)
EMP-0300 |  | Employee | Dipanshu Gupta | Associate BA | Sales | 2 | EMP-0265 | Gurjot Singh | 0 | None (employee record) |  | Dipanshu Gupta (Associate BA)
EMP-0301 |  | Employee | Pratham Arora | Associate BA | Sales | 2 | EMP-0265 | Gurjot Singh | 0 | None (employee record) |  | Pratham Arora (Associate BA)
EMP-0302 |  | Employee | Sachin Ghambir | AVP: Credit | NBFC | 1 |  |  | 4 | HOD |  | Sachin Ghambir (AVP: Credit)
EMP-0303 |  | Employee | VijayPal Singh | AVP: Collection | NBFC | 2 | EMP-0302 | Sachin Ghambir | 0 | None (employee record) |  | VijayPal Singh (AVP: Collection)
EMP-0304 |  | Employee | Mukesh Kumar | Sr. Manager Credit | NBFC | 2 | EMP-0302 | Sachin Ghambir | 0 | None (employee record) | Name shared with another record - confirm identity | Mukesh Kumar (Sr. Manager Credit)
EMP-0305 |  | Employee | DeepChaya | Manager OPS | NBFC | 2 | EMP-0302 | Sachin Ghambir | 0 | None (employee record) | Single name only - add surname | DeepChaya (Manager OPS)
EMP-0306 |  | Employee | Harpreet Singh Nurpuri | Sr. Manager Sales | NBFC | 2 | EMP-0302 | Sachin Ghambir | 3 | Manager |  | Harpreet Singh Nurpuri (Sr. Manager Sales)
EMP-0307 |  | Employee | Aashish | AM-Sales | NBFC | 3 | EMP-0306 | Harpreet Singh Nurpuri | 0 | None (employee record) | Single name only - add surname | Aashish (AM-Sales)
EMP-0308 |  | Employee | Amit Bhaskar | Manager Sales | NBFC | 3 | EMP-0306 | Harpreet Singh Nurpuri | 0 | None (employee record) |  | Amit Bhaskar (Manager Sales)
EMP-0309 |  | Employee | Vikas Singh | AM-Sales | NBFC | 3 | EMP-0306 | Harpreet Singh Nurpuri | 0 | None (employee record) |  | Vikas Singh (AM-Sales)
POS-0310 |  | Vacant Position | (vacant) | Head Insurance | Insurance | 1 |  |  | 2 | None (vacant) | Vacant / unnamed position | Head Insurance
EMP-0311 |  | Employee | Amit Arvind Gala | Sr. Territory Manager | Insurance | 2 | POS-0310 | Head Insurance | 2 | Manager | Chart text malformed (fixed) | Amit Arvind Gala (Sr. Terriotary Manager
EMP-0312 |  | Employee | Satish Shivaji | Sr. Manager- Insurance Sales | Insurance | 3 | EMP-0311 | Amit Arvind Gala | 0 | None (employee record) |  | Satish Shivaji (Sr. Manager- Insurance Sales)
EMP-0313 |  | Employee | Bhanu Dhareniya | Manager:Insurance Sales | Insurance | 3 | EMP-0311 | Amit Arvind Gala | 0 | None (employee record) |  | Bhanu Dhareniya (Manager:Insurance Sales)
EMP-0314 |  | Employee | Vikrant Sharma | Sr. Manager-Insurance | Insurance | 2 | POS-0310 | Head Insurance | 0 | None (employee record) |  | Vikrant Sharma (Sr. Manager-Insurance)
EMP-0315 |  | Employee | Dheeraj Dhiwan | Director | Admin | 1 |  |  | 3 | HOD |  | Dheeraj Dhiwan (Director)
EMP-0316 |  | Employee | Manav Vohra | Admin Manager | Admin | 2 | EMP-0315 | Dheeraj Dhiwan | 2 | Manager |  | Manav Vohra (Admin Manager)
EMP-0317 |  | Employee | Talwinder Singh | Admin Assistant | Admin | 3 | EMP-0316 | Manav Vohra | 0 | None (employee record) |  | Talwinder Singh (Admin Assistant)
EMP-0318 |  | Employee | Vinod Gupta | Admin Assistant | Admin | 3 | EMP-0316 | Manav Vohra | 0 | None (employee record) |  | Vinod Gupta (Admin Assistant)
EMP-0319 |  | Employee | Manu Partap | AM- Admin | Admin | 2 | EMP-0315 | Dheeraj Dhiwan | 0 | None (employee record) |  | Manu Partap (AM- Admin)
EMP-0320 |  | Employee | Shiv Parsad | Admin Assistant | Admin | 2 | EMP-0315 | Dheeraj Dhiwan | 0 | None (employee record) |  | Shiv Parsad (Admin Assistant)
POS-0321 |  | Vacant Position | (vacant) | Department Head (not named in chart) | Front Desk | 1 |  |  | 1 | None (vacant) | Vacant / unnamed position
EMP-0322 |  | Employee | Adeeba Khan | Team Lead | Front Desk | 2 | POS-0321 | Department Head (not named in chart) | 1 | Team Lead |  | Adeeba Khan (Team Lead)
EMP-0323 |  | Employee | Muskan | FOE | Front Desk | 3 | EMP-0322 | Adeeba Khan | 0 | None (employee record) | Name shared with another record - confirm identity; Single name only - add surname; Chart text malformed (fixed) | Muskan (FOE))

## Name_Collisions
Name | Record ID | Designation | Department | Reporting Manager | Likely same person? | Resolution (fill)
Amit Kumar | EMP-0015 | Sr. QA Engineer | Product | Vishal Sharma | No - different role/department
Amit Kumar | EMP-0266 | Manager | Sales | Gurjot Singh | No - different role/department
Amritpal Singh | EMP-0240 | CS Executive | Client Support | Neeru Arya | Possibly duplicate entry
Amritpal Singh | EMP-0252 | CS Executive | Client Support | Angel Sharma | Possibly duplicate entry
Ankit | EMP-0041 | Software Engineer | Product | Deepinder Singh | No - different role/department
Ankit | EMP-0223 | CS Executive | Client Support | Ramandeep Kaur | No - different role/department
Gurpreet Singh | EMP-0071 | Project Lead | Product | Parvinder Singh Chopra | No - different role/department
Gurpreet Singh | EMP-0161 | Manager | IT | Patel Rajesh | No - different role/department
Hardeep Singh | EMP-0198 | AM Compliance | Compliance | Akanksha Chhabra | No - different role/department
Hardeep Singh | EMP-0250 | CS Executive | Client Support | Angel Sharma | No - different role/department
Jitender Thakur | EMP-0094 | TA | HR | Himani Sharma | No - different role/department
Jitender Thakur | EMP-0179 | BO Executive | Operations & BO | Kanav Verma | No - different role/department
Maninder Singh | EMP-0083 | Sr. UI/UX Designer | Product | Pradeep Thakur | No - different role/department
Maninder Singh | EMP-0120 | SEO Executive | Digital Marketing | Naveen Kumar | No - different role/department
Mukesh Kumar | EMP-0079 | Dev Ops Engineer | Product | Parvinder Singh Chopra | No - different role/department
Mukesh Kumar | EMP-0304 | Sr. Manager Credit | NBFC | Sachin Ghambir | No - different role/department
Muskan | EMP-0038 | Software Engineer | Product | Deepinder Singh | No - different role/department
Muskan | EMP-0323 | FOE | Front Desk | Adeeba Khan | No - different role/department
Naveen Kumar | EMP-0118 | Assistant Manager | Digital Marketing | Ramneek | No - different role/department
Naveen Kumar | EMP-0204 | RMS Manager | RMS & Dealer | Ayushman Dey | No - different role/department
Neeraj Kumar | EMP-0163 | IT Executive | IT | Sourav Kumar | No - different role/department
Neeraj Kumar | EMP-0205 | Sr. RMS Executive | RMS & Dealer | Naveen Kumar | No - different role/department
Pawan Kumar | EMP-0036 | Software Engineer | Product | Deepinder Singh | No - different role/department
Pawan Kumar | EMP-0109 | AVP-Operations | Demat |  | No - different role/department
Pawan Kumar | EMP-0109 | AVP-Operations | Operations & BO |  | No - different role/department
Pawan Kumar | EMP-0109 | AVP-Operations | Compliance |  | No - different role/department
Rajesh Kumar | EMP-0155 | Sr. SEO Specialist | Digital Marketing | Ramneek | No - different role/department
Rajesh Kumar | EMP-0280 | Sr. Manager | Sales | Gurjot Singh | No - different role/department
Ramandeep Kaur | EMP-0222 | Sr. CS Executive | Client Support | Sahil Sharma | No - different role/department
Ramandeep Kaur | EMP-0283 | Sales Executive | Sales | Sakshi Sharma | No - different role/department
Sakshi Sharma | EMP-0258 | CS Executive | jUMPP CS & Sales | Priyanka Rana | No - different role/department
Sakshi Sharma | EMP-0281 | Team Lead | Sales | Rajesh Kumar | No - different role/department
Salim Khan | EMP-0206 | RMS Executive | RMS & Dealer | Naveen Kumar | Possibly duplicate entry
Salim Khan | EMP-0208 | RMS Executive | RMS & Dealer | Naveen Kumar | Possibly duplicate entry

## Departments
Department | Head Record ID | Head | Headcount (employees) | Vacant Positions | Proposed Category | Tracker Name Aliases | Notes
Sales | EMP-0265 | Gurjot Singh | 37 | 0 | Core Revenue | Sales | Direct revenue targets.
Insurance | POS-0310 | Head Insurance | 4 | 1 | Core Revenue |  | Insurance sales targets.
NBFC | EMP-0302 | Sachin Ghambir | 8 | 0 | Core Revenue |  | Sales sub-team is Core Revenue; Credit, Collection and Ops sub-teams should be overridden to Revenue-Enabling at team level.
jUMPP CS & Sales | EMP-0254 | Kapil Sachdev | 11 | 0 | Core Revenue |  | Sales team = Core Revenue; CS team overridden to Customer Service.
Product | POS-0001 | Managing Director | 71 | 1 | Revenue-Enabling | Product | Delivery on time is the primary measure.
AI | POS-0001 | Managing Director | 11 | 1 | Revenue-Enabling
Operations & BO | EMP-0109 | Pawan Kumar | 29 | 0 | Revenue-Enabling | Operations; Back ofc & Operations
Demat | EMP-0109 | Pawan Kumar | 8 | 0 | Revenue-Enabling
RMS & Dealer | EMP-0203 | Ayushman Dey | 16 | 0 | Revenue-Enabling |  | Dealer sub-team may be moved to Core Revenue if dealers carry brokerage targets.
Compliance | EMP-0109 | Pawan Kumar | 6 | 1 | Revenue-Enabling | Compliance | Compliance is the core output, so the 20% compliance weight fits.
Digital Marketing | EMP-0117 | Ramneek | 40 | 0 | Revenue-Enabling |  | Acquisition/brand targets feed Achievement %.
Client Support | EMP-0219 | Kapil Abrol | 35 | 0 | Customer Service (new) | Customer Support | CSAT is the primary measure; no original category weighted it correctly.
IT | EMP-0157 | Patel Rajesh | 12 | 0 | Support | IT / Tech
HR | EMP-0085 | Balneet Birah | 12 | 1 | Support | Human Resources; Learning & Development | L&D is a sub-team under HR.
Accounts | EMP-0098 | Aunj Ohri | 11 | 0 | Support | Finance
Admin | EMP-0315 | Dheeraj Dhiwan | 6 | 0 | Support
Front Desk | POS-0321 | Department Head (not named in chart) | 2 | 1 | Support |  | No head named in chart.
Total |  |  | 319 | 6
Note: Pawan Kumar (EMP-0109) heads Demat, Operations & BO and Compliance, and the Managing Director heads Product and AI, so the same head ID appears more than once. Headcount counts rows per department; a person who appears in two department charts is counted in both.

## Category_Weights
Metric | Core Revenue | Revenue-Enabling | Support | Customer Service (new) | Change vs R&R_Parameters_2
On-Time Rate | 20% | 30% | 20% | 20%
Achievement % | 30% | 25% | 0% | 15%
Compliance | 0% | 20% | 10% | 10%
CSAT | 25% | 0% | 0% | 30%
Quality | 15% | 15% | 25% | 25%
Productivity | 0% | 0% | 0% | 0% | Defined but unweighted in all categories; used as an R&R tie-breaker and award input. Set a weight here to activate it.
Collaboration | 10% | 10% | 25% | 0% | "Culture" in Core Revenue is mapped to Collaboration (Culture was never defined).
Innovation & Process Improvement | 0% | 0% | 20% | 0%
Total (must be 100%) | 100% | 100% | 100% | 100%
Check | OK | OK | OK | OK
The 60% Quantifiable / 40% Qualitative split in R_R_Parameters_2 is retired: its listed sub-weights summed to 75-100% and 50-65%. Category weights above are the single source of truth. Customer Service is a proposed new category and needs management approval.

## Tracker_Cleaned
Src Row | Project ID | Project | Task ID | Task / Deliverable | Assignee (as typed) | Emp ID | Assignee (resolved) | Match Note | Assignment Role | Contribution % | Department | Project Owner | Priority | Start Date | Target Date | Completed Date | Original Status | Mapped Status | Timing (auto) | Blocker Type | Delay Reason | Validated? | Excludable if Late? | On-Time Eligible (auto) | Data Quality Flags
4 | PRJ-001 | Loan Changes (Advance Salary) | PRJ-001-T01 | Loan Changes (Advance Salary) | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-24 | 2026-08-24 | 2026-08-24 | Completed | Completed | On time |  |  |  |  | Yes
5 | PRJ-002 | Trade.Shoonya Global Dashboard (Corporate actions) | PRJ-002-T01 | Trade.Shoonya Global Dashboard (Corporate actions) | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-04 | 2026-08-20 | 2026-08-20 | Completed | Completed | On time |  |  |  |  | Yes
6 | PRJ-003 | Mobile-Trade.Shoonya Global Dashboard (Corporate actions) | PRJ-003-T01 | Mobile-Trade.Shoonya Global Dashboard (Corporate actions) | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-19 | 2026-08-21 | 2026-08-21 | Completed | Completed | On time |  |  |  |  | Yes
7 | PRJ-004 | Shoonya R&R | PRJ-004-T01 | Shoonya R&R | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-07 | 2026-08-28 | 2026-08-08 | On Hold | On Hold | On time | Management reprioritisation | Working on MF | Yes | Yes | No | Has completed date but status is On Hold; Completed date kept for reference; not counted as completed
8 | PRJ-005 | Trade Shoonya: Dark theme | PRJ-005-T01 | Trade Shoonya: Dark theme | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | Medium | 2026-09-10 | 2026-09-18 |  | On Hold | On Hold | Overdue | Management reprioritisation | Working on R&R and MF | Yes | Yes | No
9 | PRJ-006 | Jumpp R&R | PRJ-006-T01 | Jumpp R&R | Harsh | EMP-0084 | Harsh | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-10 | 2026-08-14 |  | In Review | In Review | Overdue | Rework (own team feedback) | Inernal feedback incorporated | Yes | No | No
10 | PRJ-007 | Rewards Journey UI (Milestones or Campaign) | PRJ-007-T01 | Rewards Journey UI (Milestones or Campaign) | Harsh | EMP-0084 | Harsh | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-20 | 2026-08-24 | 2026-08-26 | In Review | In Review | Late |  |  |  |  | No | Has completed date but status is In Review; Completed date kept for reference; not counted as completed
11 | PRJ-008 | Digital Silver | PRJ-008-T01 | Digital Silver | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-15 | 2026-08-24 |  | In Review | In Review | Overdue |  |  |  |  | No
12 | PRJ-009 | Digital Silver SIP | PRJ-009-T01 | Digital Silver SIP | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-16 | 2026-08-25 |  | In Review | In Review | Overdue |  |  |  |  | No
13 | PRJ-010 | Digital Gold SIP | PRJ-010-T01 | Digital Gold SIP | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-17 | 2026-08-26 |  | In Review | In Review | Overdue |  |  |  |  | No
14 | PRJ-011 | Physical Silver | PRJ-011-T01 | Physical Silver | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-18 | 2026-08-27 |  | In Review | In Review | Overdue |  |  |  |  | No
15 | PRJ-012 | Physical Gold | PRJ-012-T01 | Physical Gold | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-19 | 2026-08-28 |  | In Review | In Review | Overdue |  |  |  |  | No
16 | PRJ-013 | Jumpp Website 1.1 | PRJ-013-T01 | Jumpp Website 1.1 | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-06-01 | 2026-08-31 | 2026-08-21 | On Hold | On Hold | On time | Internal dependency (other team review) | DM team feedbacks | Yes | Yes | No | Has completed date but status is On Hold; Completed date kept for reference; not counted as completed
17 | PRJ-014 | Insurance Chatbot | PRJ-014-T01 | Insurance Chatbot | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-27 | 2026-09-07 |  | Ongoing | In Progress | Overdue |  |  |  |  | No
18 | PRJ-015 | Shoonya Website Enhancements | PRJ-015-T01 | Shoonya Website Enhancements | Maninder | EMP-0083 | Maninder Singh | Context: Sr. UI/UX (not the SEO Maninder Singh) | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-27 | 2026-08-27 |  | On Hold | On Hold | Overdue | Management reprioritisation | Due to jUMPP task | Yes | Yes | No
19 | PRJ-016 | Onboarding Pan Skip Transition History UI (Need to be updated) | PRJ-016-T01 | Onboarding Pan Skip Transition History UI (Need to be updated) | Harsh | EMP-0084 | Harsh | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-25 | 2026-08-25 | 2026-08-25 | Completed | Completed | On time |  |  |  |  | Yes
20 | PRJ-017 | SensAI | PRJ-017-T01 | SensAI | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-11 | 2026-08-14 | 2026-09-01 | On Hold | On Hold | Late | Management reprioritisation | Working on R&R and MF | Yes | Yes | No | Has completed date but status is On Hold; Completed date kept for reference; not counted as completed
21 | PRJ-018 | Shoonya Bonds- Entry points and graphics UI | PRJ-018-T01 | Shoonya Bonds- Entry points and graphics UI | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-03 | 2026-08-03 |  | Completed | In Review | Overdue |  |  |  |  | No | Completed without completed date; Moved to In Review until completion date is recorded
22 | PRJ-019 | Shoonya MF | PRJ-019-T01 | Shoonya MF | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-07-02 | 2026-07-31 | 2026-09-01 | In Review | In Review | Late | Requirement change | Recived update requirement based on MF: API | Yes | Yes | No | Has completed date but status is In Review; Completed date kept for reference; not counted as completed
23 | PRJ-020 | Algo Trading mobile app | PRJ-020-T01 | Algo Trading mobile app | Sachin | EMP-0082 | Sachin Barnwal | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-08-10 | 2026-08-14 |  | In Review | In Review | Overdue |  |  |  |  | No
24 | PRJ-021 | App Tour | PRJ-021-T01 | App Tour | Harsh | EMP-0084 | Harsh | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-06-24 | 2026-06-24 |  | In Review | In Review | Overdue |  |  |  |  | No
25 | PRJ-022 | Widgets | PRJ-022-T01 | Widgets | Harsh | EMP-0084 | Harsh | Context: UI/UX under Pradeep Thakur | Owner | 100% | Product | Pradeep Thakur | High | 2026-06-24 | 2026-06-24 |  | In Review | In Review | Overdue |  |  |  |  | No
26 | PRJ-023 | MTF Interest Charges updated | PRJ-023-T01 | MTF Interest Rate changes in KORP | Vinay | EMP-0170 | Vinay Thakur | Context: Ops Executive | Owner | 100% | Operations & BO | Pawan | High | 2026-08-01 | 2026-09-01 |  | Delayed | Blocked | Overdue | Internal dependency (Product/Development) | Product team Delay |  | Yes | No | "Delayed" is now derived from dates, not a status
27 | PRJ-024 | Bond | PRJ-024-T01 | Bond Back office intigration with Exchnages | Pawan | EMP-0109 | Pawan Kumar | Context: AVP-Operations (not the Software Engineer) | Owner | 100% | Operations & BO | Pawan | High | 2026-08-18 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Product team working |  | Yes | No | Target date missing
28 | PRJ-025 | Refer and Reward | PRJ-025-T01 | for new client refer reward in KORP | pawan | EMP-0109 | Pawan Kumar | Context: AVP-Operations (not the Software Engineer) | Owner | 100% | Operations & BO | Pawan | Medium | 2026-08-10 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Product team working |  | Yes | No | Target date missing
29 | PRJ-026 | Account opening journey with (AI) incorporation | PRJ-026-T01 | New account opening journey with (AI) incorporation | Vivek | EMP-0174 | Vivek Sharma | Exact first-name match in Ops & BO | Owner | 100% | Operations & BO | Pawan | High | 2026-04-14 |  | 2026-10-13 | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | launch of p2 delayed this project |  | Yes | No | Target date missing; Completed date is in the future; Has completed date but status is Delayed; "Delayed" is now derived from dates, not a status
30 | PRJ-026 | Account opening journey with (AI) incorporation | PRJ-026-T01 | New account opening journey with (AI) incorporation | Jaidev | EMP-0181 | Jai Dev Singh | Spelling differs (Jaidev vs Jai Dev) | Owner | 100% | Operations & BO | Vivek | High | 2026-04-14 |  | 2026-10-13 | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | launch of p2 delayed this project |  | Yes | No | Target date missing; Completed date is in the future; Has completed date but status is Delayed; "Delayed" is now derived from dates, not a status
31 | PRJ-027 | (AI) integrated Module for Prism Dashboard (BO) | PRJ-027-T01 | BO Daily MIS | Vivek | EMP-0174 | Vivek Sharma | Exact first-name match in Ops & BO | Owner | 100% | Operations & BO | Pawan | Medium | 2026-08-03 | 2026-08-31 |  | Ongoing | In Progress | Overdue |  |  |  |  | No
32 | PRJ-027 | (AI) integrated Module for Prism Dashboard (BO) | PRJ-027-T01 | BO Daily MIS | Jaidev | EMP-0181 | Jai Dev Singh | Spelling differs (Jaidev vs Jai Dev) | Owner | 100% | Operations & BO | Vivek | Medium | 2026-08-03 | 2026-08-31 |  | Ongoing | In Progress | Overdue |  |  |  |  | No
33 | PRJ-027 | (AI) integrated Module for Prism Dashboard (BO) | PRJ-027-T01 | BO Daily MIS | Kanav | EMP-0175 | Kanav Verma | Exact first-name match | Owner | 100% | Operations & BO | Vivek | Medium | 2026-08-03 | 2026-08-31 |  | Ongoing | In Progress | Overdue |  |  |  |  | No
34 | PRJ-027 | (AI) integrated Module for Prism Dashboard (BO) | PRJ-027-T01 | BO Daily MIS | Akash | EMP-0187 | Akashdeep | Probable: Akashdeep (BO Team Lead) - confirm | Owner | 100% | Operations & BO | Vivek | Medium | 2026-08-03 | 2026-08-31 |  | Ongoing | In Progress | Overdue |  |  |  |  | No
35 | PRJ-028 | Quick Pledge/Unpledge | PRJ-028-T01 | Auto process for Pledge/Unpledge | Yogesh | EMP-0110 | Yogesh | Exact match | Owner | 100% | Operations & BO | Pawan | High | 2026-06-30 | 2026-09-11 |  | Ongoing | In Progress | Overdue | Internal dependency (Product/Development) | Product team working |  | Yes | No
36 | PRJ-028 | Quick Pledge/Unpledge | PRJ-028-T01 | Auto process for Pledge/Unpledge | Atul | EMP-0112 | Atul Kumar | Context: reports to Yogesh (Demat) | Owner | 100% | Operations & BO | Yogesh | High | 2026-06-30 | 2026-09-11 |  | Ongoing | In Progress | Overdue | Internal dependency (Product/Development) | Product team working |  | Yes | No
37 | PRJ-029 | Buyback Feature Implementation | PRJ-029-T01 | Auto process for Buyback | Yogesh | EMP-0110 | Yogesh | Exact match | Owner | 100% | Operations & BO | Pawan | Medium | 2026-08-01 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Product team working |  | Yes | No | Target date missing
38 | PRJ-029 | Buyback Feature Implementation | PRJ-029-T01 | Auto process for Buyback | Atul | EMP-0112 | Atul Kumar | Context: reports to Yogesh (Demat) | Owner | 100% | Operations & BO | Yogesh | Medium | 2026-08-01 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Product team working |  | Yes | No | Target date missing
39 | PRJ-030 | SenS-AI 1.1 Enhancement | PRJ-030-T01 | Development of Module in Mobile app | Saksham | EMP-0048 | Saksham | Exact match | Contributor | 20% | Product |  | High |  | 2026-09-03 |  | Delayed | Blocked | Overdue | Management reprioritisation | due to an urgent requirement, we are releasing changes to MTF 3x the app is in review and once that app is released, we will publish SensAI |  | Yes | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
39 | PRJ-030 | SenS-AI 1.1 Enhancement | PRJ-030-T01 | Development of Module in Mobile app | Jaspreet | EMP-0058 | Jaspreet Singh | Exact first-name match | Contributor | 20% | Product |  | High |  | 2026-09-03 |  | Delayed | Blocked | Overdue | Management reprioritisation | due to an urgent requirement, we are releasing changes to MTF 3x the app is in review and once that app is released, we will publish SensAI |  | Yes | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
39 | PRJ-030 | SenS-AI 1.1 Enhancement | PRJ-030-T01 | Development of Module in Mobile app | Jatin | EMP-0046 | Jatin Vashisht | Exact first-name match | Contributor | 20% | Product |  | High |  | 2026-09-03 |  | Delayed | Blocked | Overdue | Management reprioritisation | due to an urgent requirement, we are releasing changes to MTF 3x the app is in review and once that app is released, we will publish SensAI |  | Yes | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
39 | PRJ-030 | SenS-AI 1.1 Enhancement | PRJ-030-T01 | Development of Module in Mobile app | Aryan | EMP-0027 | Aryan Raj | Exact first-name match | Contributor | 20% | Product |  | High |  | 2026-09-03 |  | Delayed | Blocked | Overdue | Management reprioritisation | due to an urgent requirement, we are releasing changes to MTF 3x the app is in review and once that app is released, we will publish SensAI |  | Yes | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
39 | PRJ-030 | SenS-AI 1.1 Enhancement | PRJ-030-T01 | Development of Module in Mobile app | sumit roy | EMP-0024 | Sumit Roy | Exact match | Contributor | 20% | Product |  | High |  | 2026-09-03 |  | Delayed | Blocked | Overdue | Management reprioritisation | due to an urgent requirement, we are releasing changes to MTF 3x the app is in review and once that app is released, we will publish SensAI |  | Yes | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
40 | PRJ-031 | fno Edge | PRJ-031-T01 | integration of fnoedge sdk | sumit kumar | EMP-0057 | Sumit Kumar | Exact match | Contributor | 25% | Product |  | High |  | 2026-08-27 |  | Completed | In Review | Overdue |  |  |  |  | No | Project owner missing; Completed without completed date; Moved to In Review until completion date is recorded; Multiple assignees in one cell - split; confirm owner and contribution %
40 | PRJ-031 | fno Edge | PRJ-031-T01 | integration of fnoedge sdk | tushar | EMP-0052 | Tushar Verma | Exact first-name match | Contributor | 25% | Product |  | High |  | 2026-08-27 |  | Completed | In Review | Overdue |  |  |  |  | No | Project owner missing; Completed without completed date; Moved to In Review until completion date is recorded; Multiple assignees in one cell - split; confirm owner and contribution %
40 | PRJ-031 | fno Edge | PRJ-031-T01 | integration of fnoedge sdk | Jatin | EMP-0046 | Jatin Vashisht | Exact first-name match | Contributor | 25% | Product |  | High |  | 2026-08-27 |  | Completed | In Review | Overdue |  |  |  |  | No | Project owner missing; Completed without completed date; Moved to In Review until completion date is recorded; Multiple assignees in one cell - split; confirm owner and contribution %
40 | PRJ-031 | fno Edge | PRJ-031-T01 | integration of fnoedge sdk | Sumit Roy | EMP-0024 | Sumit Roy | Exact match | Contributor | 25% | Product |  | High |  | 2026-08-27 |  | Completed | In Review | Overdue |  |  |  |  | No | Project owner missing; Completed without completed date; Moved to In Review until completion date is recorded; Multiple assignees in one cell - split; confirm owner and contribution %
41 | PRJ-032 | Automating the current PRISM process | PRJ-032-T01 | automating the onboarding process by ingrating AI APIs | Shivam | EMP-0042 | Shivam | Exact match | Contributor | 33.33% | Product |  | Medium |  | 2026-10-13 |  | Ongoing | In Progress | Open |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
41 | PRJ-032 | Automating the current PRISM process | PRJ-032-T01 | automating the onboarding process by ingrating AI APIs | Ankit | EMP-0041 | Ankit | Probable: Ankit (Software Engineer, Product) - 2 records named Ankit | Contributor | 33.33% | Product |  | Medium |  | 2026-10-13 |  | Ongoing | In Progress | Open |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
41 | PRJ-032 | Automating the current PRISM process | PRJ-032-T01 | automating the onboarding process by ingrating AI APIs | Manisha | EMP-0025 | Manisha Kumari | Exact first-name match | Contributor | 33.33% | Product |  | Medium |  | 2026-10-13 |  | Ongoing | In Progress | Open |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
42 | PRJ-033 | MTF Margin increase | PRJ-033-T01 | content changes to web page & Mobile apps | Ankit Grin |  | Ankit Grin | NOT IN ORG CHART - add to master | Contributor | 33.33% | Product |  | High | 2026-09-03 | 2026-09-05 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %; Assignee not in org chart
42 | PRJ-033 | MTF Margin increase | PRJ-033-T01 | content changes to web page & Mobile apps | sumit kumar | EMP-0057 | Sumit Kumar | Exact match | Contributor | 33.33% | Product |  | High | 2026-09-03 | 2026-09-05 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
42 | PRJ-033 | MTF Margin increase | PRJ-033-T01 | content changes to web page & Mobile apps | tushar | EMP-0052 | Tushar Verma | Exact first-name match | Contributor | 33.33% | Product |  | High | 2026-09-03 | 2026-09-05 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
43 | PRJ-034 | Build API / Algo Trading landing page (Shoonya) | PRJ-034-T01 | development of web page in shoonya website | Ankit Grin |  | Ankit Grin | NOT IN ORG CHART - add to master | Contributor | 50% | Product |  | High | 2026-09-03 | 2026-09-03 |  | Delayed | In Progress | Overdue |  |  |  |  | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %; Assignee not in org chart
43 | PRJ-034 | Build API / Algo Trading landing page (Shoonya) | PRJ-034-T01 | development of web page in shoonya website | Aryan | EMP-0027 | Aryan Raj | Exact first-name match | Contributor | 50% | Product |  | High | 2026-09-03 | 2026-09-03 |  | Delayed | In Progress | Overdue |  |  |  |  | No | Project owner missing; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
44 | PRJ-035 | Backend will push market data as user attributes for all users, updated 4 times daily, enabling automated and broadcast push notifications | PRJ-035-T01 | api integration for pushing the notifications | Amandeep |  | Amandeep | NOT IN ORG CHART - add to master | Contributor | 33.33% | Product |  | High | 2026-08-19 | 2026-09-03 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %; Assignee not in org chart
44 | PRJ-035 | Backend will push market data as user attributes for all users, updated 4 times daily, enabling automated and broadcast push notifications | PRJ-035-T01 | api integration for pushing the notifications | Sukriti | EMP-0026 | Sukriti | Exact match | Contributor | 33.33% | Product |  | High | 2026-08-19 | 2026-09-03 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
44 | PRJ-035 | Backend will push market data as user attributes for all users, updated 4 times daily, enabling automated and broadcast push notifications | PRJ-035-T01 | api integration for pushing the notifications | Sumit Kumar | EMP-0057 | Sumit Kumar | Exact match | Contributor | 33.33% | Product |  | High | 2026-08-19 | 2026-09-03 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Project owner missing; Multiple assignees in one cell - split; confirm owner and contribution %
45 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T01 | Sourcing; KPI setup; dashboards; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 | 2026-06-11 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
45 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T01 | Sourcing; KPI setup; dashboards; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 | 2026-06-11 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
45 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T01 | Sourcing; KPI setup; dashboards; | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 | 2026-06-11 |  | Ongoing | In Progress | Overdue |  |  |  |  | No | Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
46 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T02 | CSAT optimization; bot integration; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
46 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T02 | CSAT optimization; bot integration; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
46 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T02 | CSAT optimization; bot integration; | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
47 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T03 | APIs; CRM implementation; channel-wise RTM | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
47 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T03 | APIs; CRM implementation; channel-wise RTM | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
47 | PRJ-036 | CRM Sourcing, Testing & Implementation | PRJ-036-T03 | APIs; CRM implementation; channel-wise RTM | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-03-06 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
48 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T01 | Calling bot; chat bot; email bot; FAQs; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
48 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T01 | Calling bot; chat bot; email bot; FAQs; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
48 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T01 | Calling bot; chat bot; email bot; FAQs; | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
49 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T02 | BRDs and documentation; database upload; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
49 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T02 | BRDs and documentation; database upload; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
49 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T02 | BRDs and documentation; database upload; | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
50 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T03 | final implementation sign-off | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
50 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T03 | final implementation sign-off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
50 | PRJ-037 | AI Bots Testing & Implementation | PRJ-037-T03 | final implementation sign-off | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
51 | PRJ-038 | AI Triage Process | PRJ-038-T01 | Process creation; phased testing; sign-off; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
51 | PRJ-038 | AI Triage Process | PRJ-038-T01 | Process creation; phased testing; sign-off; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
51 | PRJ-038 | AI Triage Process | PRJ-038-T01 | Process creation; phased testing; sign-off; | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
52 | PRJ-038 | AI Triage Process | PRJ-038-T02 | phased implementation across contact drivers | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
52 | PRJ-038 | AI Triage Process | PRJ-038-T02 | phased implementation across contact drivers | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
52 | PRJ-038 | AI Triage Process | PRJ-038-T02 | phased implementation across contact drivers | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
53 | PRJ-039 | QA & ATA Audit Platform | PRJ-039-T01 | QA audit portal; ATA portal; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
53 | PRJ-039 | QA & ATA Audit Platform | PRJ-039-T01 | QA audit portal; ATA portal; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
54 | PRJ-039 | QA & ATA Audit Platform | PRJ-039-T02 | Database testing; dashboards; | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
54 | PRJ-039 | QA & ATA Audit Platform | PRJ-039-T02 | Database testing; dashboards; | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
55 | PRJ-039 | QA & ATA Audit Platform | PRJ-039-T03 | agent feedback emails; dispute framework and portal | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
55 | PRJ-039 | QA & ATA Audit Platform | PRJ-039-T03 | agent feedback emails; dispute framework and portal | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
56 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T01 | CSAT data lake testing | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
56 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T01 | CSAT data lake testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
56 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T01 | CSAT data lake testing | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
57 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T02 | ACPT portal; ATA for ACPT | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
57 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T02 | ACPT portal; ATA for ACPT | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
57 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T02 | ACPT portal; ATA for ACPT | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
58 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T03 | automated WTD and MTD reporting | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
58 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T03 | automated WTD and MTD reporting | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
58 | PRJ-040 | CSAT & ACPT Audit and Reporting Platform | PRJ-040-T03 | automated WTD and MTD reporting | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 33.33% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
59 | PRJ-041 | Training Portal & Executive CSAT Reporting | PRJ-041-T01 | Training and tests portal | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
59 | PRJ-041 | Training Portal & Executive CSAT Reporting | PRJ-041-T01 | Training and tests portal | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
60 | PRJ-041 | Training Portal & Executive CSAT Reporting | PRJ-041-T02 | Session recording; coverage emails | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
60 | PRJ-041 | Training Portal & Executive CSAT Reporting | PRJ-041-T02 | Session recording; coverage emails | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
61 | PRJ-041 | Training Portal & Executive CSAT Reporting | PRJ-041-T03 | Executive CSAT dashboards | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
61 | PRJ-041 | Training Portal & Executive CSAT Reporting | PRJ-041-T03 | Executive CSAT dashboards | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-25 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
62 | PRJ-042 | Mutual Fund mandate issue | PRJ-042-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2024-11-18 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review
63 | PRJ-042 | Mutual Fund mandate issue | PRJ-042-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2024-11-18 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review
64 | PRJ-042 | Mutual Fund mandate issue | PRJ-042-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2024-11-18 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review
65 | PRJ-043 | Multiple Issues in Enable Exchange KYC | PRJ-043-T01 | Design, Testing | Neeru Arya | EMP-0239 | Neeru Arya | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2025-06-19 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
65 | PRJ-043 | Multiple Issues in Enable Exchange KYC | PRJ-043-T01 | Design, Testing | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2025-06-19 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
66 | PRJ-043 | Multiple Issues in Enable Exchange KYC | PRJ-043-T02 | Co-ordination with product | Neeru Arya | EMP-0239 | Neeru Arya | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2025-06-19 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
66 | PRJ-043 | Multiple Issues in Enable Exchange KYC | PRJ-043-T02 | Co-ordination with product | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2025-06-19 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
67 | PRJ-043 | Multiple Issues in Enable Exchange KYC | PRJ-043-T03 | Implementation sign off | Neeru Arya | EMP-0239 | Neeru Arya | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2025-06-19 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
67 | PRJ-043 | Multiple Issues in Enable Exchange KYC | PRJ-043-T03 | Implementation sign off | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2025-06-19 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
68 | PRJ-044 | Chart issues | PRJ-044-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2025-08-05 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review
69 | PRJ-044 | Chart issues | PRJ-044-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2025-08-05 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review
70 | PRJ-044 | Chart issues | PRJ-044-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2025-08-05 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Open > 6 months - review
71 | PRJ-045 | Introduction of Time-Based Validity Order Types | PRJ-045-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-02-19 |  |  | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
71 | PRJ-045 | Introduction of Time-Based Validity Order Types | PRJ-045-T01 | Design, Testing | Aaina | EMP-0224 | Aaina Ghill | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-02-19 |  |  | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
72 | PRJ-045 | Introduction of Time-Based Validity Order Types | PRJ-045-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-02-19 |  |  | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
72 | PRJ-045 | Introduction of Time-Based Validity Order Types | PRJ-045-T02 | Co-ordination with product | Aaina | EMP-0224 | Aaina Ghill | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-02-19 |  |  | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
73 | PRJ-045 | Introduction of Time-Based Validity Order Types | PRJ-045-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-02-19 |  |  | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
73 | PRJ-045 | Introduction of Time-Based Validity Order Types | PRJ-045-T03 | Implementation sign off | Aaina | EMP-0224 | Aaina Ghill | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-02-19 |  |  | Delayed | Blocked | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status; Multiple assignees in one cell - split; confirm owner and contribution %
74 | PRJ-046 | Incorrect update on App Store for Brokerage Charges | PRJ-046-T01 | Design, Testing | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Owner | 100% | Client Support | Kapil Abrol |  | 2026-01-15 |  |  | Delayed | In Progress | No deadline |  |  |  |  | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status
75 | PRJ-046 | Incorrect update on App Store for Brokerage Charges | PRJ-046-T02 | Co-ordination with product | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Owner | 100% | Client Support | Kapil Abrol |  | 2026-01-15 |  |  | Delayed | In Progress | No deadline |  |  |  |  | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status
76 | PRJ-046 | Incorrect update on App Store for Brokerage Charges | PRJ-046-T03 | Implementation sign off | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Owner | 100% | Client Support | Kapil Abrol |  | 2026-01-15 |  |  | Delayed | In Progress | No deadline |  |  |  |  | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status
77 | PRJ-047 | Daily & Monthly PNL Report | PRJ-047-T01 | Design, Testing | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-03-18 |  |  | Not Started | Not Started | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
77 | PRJ-047 | Daily & Monthly PNL Report | PRJ-047-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-03-18 |  |  | Not Started | Not Started | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
78 | PRJ-047 | Daily & Monthly PNL Report | PRJ-047-T02 | Co-ordination with product | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-03-18 |  |  | Not Started | Not Started | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
78 | PRJ-047 | Daily & Monthly PNL Report | PRJ-047-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-03-18 |  |  | Not Started | Not Started | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
79 | PRJ-047 | Daily & Monthly PNL Report | PRJ-047-T03 | Implementation sign off | Adity | EMP-0237 | Adity Chiba | First name only | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-03-18 |  |  | Not Started | Not Started | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
79 | PRJ-047 | Daily & Monthly PNL Report | PRJ-047-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-03-18 |  |  | Not Started | Not Started | No deadline | Internal dependency (Product/Development) | Pending at development P2 |  | Yes | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; Multiple assignees in one cell - split; confirm owner and contribution %
80 | PRJ-048 | Frequency is not available for Mutual fund SIP | PRJ-048-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-04-01 |  |  | Delayed | In Progress | No deadline | Technical issue | Frequecy option NA during weekends |  | No | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status
81 | PRJ-048 | Frequency is not available for Mutual fund SIP | PRJ-048-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-04-01 |  |  | Delayed | In Progress | No deadline | Technical issue | Frequecy option NA during weekends |  | No | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status
82 | PRJ-048 | Frequency is not available for Mutual fund SIP | PRJ-048-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-04-01 |  |  | Delayed | In Progress | No deadline | Technical issue | Frequecy option NA during weekends |  | No | No | Target date missing; Priority missing (mandatory); Open > 6 months - review; "Delayed" is now derived from dates, not a status
83 | PRJ-049 | Mismatch LTP on Shoonya - Options before 9.15am | PRJ-049-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-04-21 |  |  | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory)
84 | PRJ-049 | Mismatch LTP on Shoonya - Options before 9.15am | PRJ-049-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-04-21 |  |  | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory)
85 | PRJ-049 | Mismatch LTP on Shoonya - Options before 9.15am | PRJ-049-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-04-21 |  |  | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory)
86 | PRJ-050 | EGR - EGR Segment Enablement on Shoonya Platform | PRJ-050-T01 | Design, Testing | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Owner | 100% | Client Support | Kapil Abrol |  | 2026-05-12 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
87 | PRJ-050 | EGR - EGR Segment Enablement on Shoonya Platform | PRJ-050-T02 | Co-ordination with product | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Owner | 100% | Client Support | Kapil Abrol |  | 2026-05-12 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
88 | PRJ-050 | EGR - EGR Segment Enablement on Shoonya Platform | PRJ-050-T03 | Implementation sign off | Adity Chhiba | EMP-0237 | Adity Chiba | Spelling differs (Chhiba vs Chiba) | Owner | 100% | Client Support | Kapil Abrol |  | 2026-05-12 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
89 | PRJ-051 | Best Price Execution of Equity Trades | PRJ-051-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-19 |  | 2026-08-20 | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing; Multiple assignees in one cell - split; confirm owner and contribution %
89 | PRJ-051 | Best Price Execution of Equity Trades | PRJ-051-T01 | Design, Testing | Jaspal | EMP-0230 | Jaspal | Context: Client Support Team Lead (not Jaspal Kaur, jUMPP) | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-19 |  | 2026-08-20 | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing; Multiple assignees in one cell - split; confirm owner and contribution %
90 | PRJ-051 | Best Price Execution of Equity Trades | PRJ-051-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-19 |  | 2026-08-20 | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing; Multiple assignees in one cell - split; confirm owner and contribution %
90 | PRJ-051 | Best Price Execution of Equity Trades | PRJ-051-T02 | Co-ordination with product | Jaspal | EMP-0230 | Jaspal | Context: Client Support Team Lead (not Jaspal Kaur, jUMPP) | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-19 |  | 2026-08-20 | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing; Multiple assignees in one cell - split; confirm owner and contribution %
91 | PRJ-051 | Best Price Execution of Equity Trades | PRJ-051-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-19 |  | 2026-08-20 | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing; Multiple assignees in one cell - split; confirm owner and contribution %
91 | PRJ-051 | Best Price Execution of Equity Trades | PRJ-051-T03 | Implementation sign off | Jaspal | EMP-0230 | Jaspal | Context: Client Support Team Lead (not Jaspal Kaur, jUMPP) | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-05-19 |  | 2026-08-20 | Ongoing | In Progress | No deadline | Not a blocker - status note |  |  |  | No | Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing; Multiple assignees in one cell - split; confirm owner and contribution %
92 | PRJ-052 | BSE IPO – Users are continuously encountering issues intermittently over a period of time. | PRJ-052-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-02 |  | 2026-08-24 | Completed | Completed | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
93 | PRJ-052 | BSE IPO – Users are continuously encountering issues intermittently over a period of time. | PRJ-052-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-02 |  | 2026-08-24 | Completed | Completed | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
94 | PRJ-052 | BSE IPO – Users are continuously encountering issues intermittently over a period of time. | PRJ-052-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-02 |  | 2026-08-24 | Completed | Completed | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
95 | PRJ-053 | IOS - Auto logout | PRJ-053-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-02 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
96 | PRJ-053 | IOS - Auto logout | PRJ-053-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-02 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
97 | PRJ-053 | IOS - Auto logout | PRJ-053-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-02 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
98 | PRJ-054 | MF Redemption VIA e-DIS. | PRJ-054-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-10 |  |  | Ongoing | In Progress | No deadline | Technical issue | Issue with fractional quantity redemeption |  | No | No | Target date missing; Priority missing (mandatory)
99 | PRJ-054 | MF Redemption VIA e-DIS. | PRJ-054-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-10 |  |  | Ongoing | In Progress | No deadline | Technical issue | Issue with fractional quantity redemeption |  | No | No | Target date missing; Priority missing (mandatory)
100 | PRJ-054 | MF Redemption VIA e-DIS. | PRJ-054-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-10 |  |  | Ongoing | In Progress | No deadline | Technical issue | Issue with fractional quantity redemeption |  | No | No | Target date missing; Priority missing (mandatory)
101 | PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | PRJ-055-T01 | Design, Testing | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-06-17 |  |  | Not Started | Not Started | No deadline | No update from owner | No update |  | No | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
101 | PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | PRJ-055-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-06-17 |  |  | Not Started | Not Started | No deadline | No update from owner | No update |  | No | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
102 | PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | PRJ-055-T02 | Co-ordination with product | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-06-17 |  |  | Not Started | Not Started | No deadline | No update from owner | No update |  | No | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
102 | PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | PRJ-055-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-06-17 |  |  | Not Started | Not Started | No deadline | No update from owner | No update |  | No | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
103 | PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | PRJ-055-T03 | Implementation sign off | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-06-17 |  |  | Not Started | Not Started | No deadline | No update from owner | No update |  | No | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
103 | PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | PRJ-055-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-06-17 |  |  | Not Started | Not Started | No deadline | No update from owner | No update |  | No | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
104 | PRJ-056 | False Order Notifications on Shoonya | PRJ-056-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-29 |  | 2026-09-04 | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing
105 | PRJ-056 | False Order Notifications on Shoonya | PRJ-056-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-29 |  | 2026-09-04 | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing
106 | PRJ-056 | False Order Notifications on Shoonya | PRJ-056-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-29 |  | 2026-09-04 | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory); Has completed date but status is Ongoing
107 | PRJ-057 | Prism 2 - Post P2 Go-Live – Feedback & Issues | PRJ-057-T01 | Design, Testing | Neeru Arya | EMP-0239 | Neeru Arya | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-30 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
108 | PRJ-057 | Prism 2 - Post P2 Go-Live – Feedback & Issues | PRJ-057-T02 | Co-ordination with product | Neeru Arya | EMP-0239 | Neeru Arya | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-30 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
109 | PRJ-057 | Prism 2 - Post P2 Go-Live – Feedback & Issues | PRJ-057-T03 | Implementation sign off | Neeru Arya | EMP-0239 | Neeru Arya | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-30 |  |  | Ongoing | In Progress | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
110 | PRJ-058 | Live IB calls not landing | PRJ-058-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-30 |  | 2026-08-10 | Completed | Completed | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
111 | PRJ-058 | Live IB calls not landing | PRJ-058-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-30 |  | 2026-08-10 | Completed | Completed | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
112 | PRJ-058 | Live IB calls not landing | PRJ-058-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-06-30 |  | 2026-08-10 | Completed | Completed | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory)
113 | PRJ-059 | HDFC Transaction List not available | PRJ-059-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-07-16 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Pending with Development |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory)
114 | PRJ-059 | HDFC Transaction List not available | PRJ-059-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-07-16 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Pending with Development |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory)
115 | PRJ-059 | HDFC Transaction List not available | PRJ-059-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Owner | 100% | Client Support | Kapil Abrol |  | 2026-07-16 |  |  | Ongoing | In Progress | No deadline | Internal dependency (Product/Development) | Pending with Development |  | Yes | No | Target date was "-" - cleared; Target date missing; Priority missing (mandatory)
116 | PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | PRJ-060-T01 | Design, Testing | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-07-28 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
116 | PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | PRJ-060-T01 | Design, Testing | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-07-28 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
117 | PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | PRJ-060-T02 | Co-ordination with product | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-07-28 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
117 | PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | PRJ-060-T02 | Co-ordination with product | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-07-28 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
118 | PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | PRJ-060-T03 | Implementation sign off | Angel Sharma | EMP-0220 | Angel Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-07-28 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %
118 | PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | PRJ-060-T03 | Implementation sign off | Sahil Sharma | EMP-0221 | Sahil Sharma | Exact match | Contributor | 50% | Client Support | Kapil Abrol |  | 2026-07-28 |  |  | Not Started | Not Started | No deadline |  |  |  |  | No | Target date missing; Priority missing (mandatory); Multiple assignees in one cell - split; confirm owner and contribution %

## Project_Register
Project ID | Project | Department | Owner | Priority | Assignment Rows | Completed | Blocked | Late/Overdue | Missing Deadline | Flags
PRJ-001 | Loan Changes (Advance Salary) | Product | Pradeep Thakur | High | 1 | 1 | 0 | 0 | 0
PRJ-002 | Trade.Shoonya Global Dashboard (Corporate actions) | Product | Pradeep Thakur | High | 1 | 1 | 0 | 0 | 0
PRJ-003 | Mobile-Trade.Shoonya Global Dashboard (Corporate actions) | Product | Pradeep Thakur | High | 1 | 1 | 0 | 0 | 0
PRJ-004 | Shoonya R&R | Product | Pradeep Thakur | High | 1 | 0 | 0 | 0 | 0
PRJ-005 | Trade Shoonya: Dark theme | Product | Pradeep Thakur | Medium | 1 | 0 | 0 | 1 | 0
PRJ-006 | Jumpp R&R | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-007 | Rewards Journey UI (Milestones or Campaign) | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-008 | Digital Silver | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-009 | Digital Silver SIP | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-010 | Digital Gold SIP | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-011 | Physical Silver | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-012 | Physical Gold | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-013 | Jumpp Website 1.1 | Product | Pradeep Thakur | High | 1 | 0 | 0 | 0 | 0
PRJ-014 | Insurance Chatbot | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-015 | Shoonya Website Enhancements | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-016 | Onboarding Pan Skip Transition History UI (Need to be updated) | Product | Pradeep Thakur | High | 1 | 1 | 0 | 0 | 0
PRJ-017 | SensAI | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-018 | Shoonya Bonds- Entry points and graphics UI | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-019 | Shoonya MF | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-020 | Algo Trading mobile app | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-021 | App Tour | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-022 | Widgets | Product | Pradeep Thakur | High | 1 | 0 | 0 | 1 | 0
PRJ-023 | MTF Interest Charges updated | Operations & BO | Pawan | High | 1 | 0 | 1 | 1 | 0
PRJ-024 | Bond | Operations & BO | Pawan | High | 1 | 0 | 0 | 0 | 1
PRJ-025 | Refer and Reward | Operations & BO | Pawan | Medium | 1 | 0 | 0 | 0 | 1
PRJ-026 | Account opening journey with (AI) incorporation | Operations & BO | Pawan | High | 2 | 0 | 2 | 0 | 2
PRJ-027 | (AI) integrated Module for Prism Dashboard (BO) | Operations & BO | Pawan | Medium | 4 | 0 | 0 | 4 | 0
PRJ-028 | Quick Pledge/Unpledge | Operations & BO | Pawan | High | 2 | 0 | 0 | 2 | 0
PRJ-029 | Buyback Feature Implementation | Operations & BO | Pawan | Medium | 2 | 0 | 0 | 0 | 2
PRJ-030 | SenS-AI 1.1 Enhancement | Product |  | High | 5 | 0 | 5 | 5 | 0 | Set owner
PRJ-031 | fno Edge | Product |  | High | 4 | 0 | 0 | 4 | 0 | Set owner
PRJ-032 | Automating the current PRISM process | Product |  | Medium | 3 | 0 | 0 | 0 | 0 | Set owner
PRJ-033 | MTF Margin increase | Product |  | High | 3 | 0 | 0 | 3 | 0 | Set owner
PRJ-034 | Build API / Algo Trading landing page (Shoonya) | Product |  | High | 2 | 0 | 0 | 2 | 0 | Set owner
PRJ-035 | Backend will push market data as user attributes for all users, updated 4 times daily, enabling automated and broadcast push notifications | Product |  | High | 3 | 0 | 0 | 3 | 0 | Set owner
PRJ-036 | CRM Sourcing, Testing & Implementation | Client Support | Kapil Abrol |  | 9 | 0 | 0 | 3 | 6 | Set priority
PRJ-037 | AI Bots Testing & Implementation | Client Support | Kapil Abrol |  | 9 | 0 | 0 | 0 | 9 | Set priority
PRJ-038 | AI Triage Process | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-039 | QA & ATA Audit Platform | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-040 | CSAT & ACPT Audit and Reporting Platform | Client Support | Kapil Abrol |  | 9 | 0 | 0 | 0 | 9 | Set priority
PRJ-041 | Training Portal & Executive CSAT Reporting | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-042 | Mutual Fund mandate issue | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-043 | Multiple Issues in Enable Exchange KYC | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-044 | Chart issues | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-045 | Introduction of Time-Based Validity Order Types | Client Support | Kapil Abrol |  | 6 | 0 | 6 | 0 | 6 | Set priority
PRJ-046 | Incorrect update on App Store for Brokerage Charges | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-047 | Daily & Monthly PNL Report | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-048 | Frequency is not available for Mutual fund SIP | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-049 | Mismatch LTP on Shoonya - Options before 9.15am | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-050 | EGR - EGR Segment Enablement on Shoonya Platform | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-051 | Best Price Execution of Equity Trades | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-052 | BSE IPO – Users are continuously encountering issues intermittently over a period of time. | Client Support | Kapil Abrol |  | 3 | 3 | 0 | 0 | 3 | Set priority
PRJ-053 | IOS - Auto logout | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-054 | MF Redemption VIA e-DIS. | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-055 | Shoonya Web Calculator – Incorrect Display of Shares Instead of Lots | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority
PRJ-056 | False Order Notifications on Shoonya | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-057 | Prism 2 - Post P2 Go-Live – Feedback & Issues | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-058 | Live IB calls not landing | Client Support | Kapil Abrol |  | 3 | 3 | 0 | 0 | 3 | Set priority
PRJ-059 | HDFC Transaction List not available | Client Support | Kapil Abrol |  | 3 | 0 | 0 | 0 | 3 | Set priority
PRJ-060 | MTF Activation Flow Revamp & User Journey Enhancement | Client Support | Kapil Abrol |  | 6 | 0 | 0 | 0 | 6 | Set priority

## OnTime_Recalc
Emp ID | Name | Department | Assignments | Eligible Completed | Completed On Time | Late (counted) | Excluded (validated delay) | Corrected On-Time Rate | On-Time Score (0-100) | Old Sheet "SLA/TAT" Value | Why it changed
EMP-0082 | Sachin Barnwal | Product | 9 | 3 | 3 | 0 | 0 | 100% | 100 | 66.67% | Old sheet counted On Hold / In Review tasks that had a completed date (SensAI, Shoonya MF, Shoonya R&R) and penalised the validated reprioritisation delay.
EMP-0084 | Harsh | Product | 5 | 1 | 1 | 0 | 0 | Insufficient Data | Insufficient Data | 50% | Rewards Journey UI is still In Review, so it is not yet a completed task.
EMP-0083 | Maninder Singh | Product | 8 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data | 100% | Jumpp Website 1.1 is On Hold; it was counted as an on-time completion. No completed tasks remain, so the metric is Insufficient Data.
EMP-0170 | Vinay Thakur | Operations & BO | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0109 | Pawan Kumar | Demat | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0174 | Vivek Sharma | Operations & BO | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0181 | Jai Dev Singh | Operations & BO | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0175 | Kanav Verma | Operations & BO | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0187 | Akashdeep | Operations & BO | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0110 | Yogesh | Demat | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0112 | Atul Kumar | Demat | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0048 | Saksham | Product | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0058 | Jaspreet Singh | Product | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0046 | Jatin Vashisht | Product | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0027 | Aryan Raj | Product | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0024 | Sumit Roy | Product | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0057 | Sumit Kumar | Product | 3 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0052 | Tushar Verma | Product | 2 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0042 | Shivam | Product | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0041 | Ankit | Product | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0025 | Manisha Kumari | Product | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0026 | Sukriti | Product | 1 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0220 | Angel Sharma | Client Support | 23 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0221 | Sahil Sharma | Client Support | 62 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0237 | Adity Chiba | Client Support | 23 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0239 | Neeru Arya | Client Support | 6 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0224 | Aaina Ghill | Client Support | 3 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
EMP-0230 | Jaspal | Client Support | 3 | 0 | 0 | 0 | 0 | Insufficient Data | Insufficient Data
Rules: eligible = Mapped Status Completed + target date + completed date. Late tasks with a validated, excludable blocker are removed from the denominator. Minimum 3 eligible tasks per period, else Insufficient Data (configurable). Score: 95%+ = 100; 75% = 60; linear between and below (floor 0) - replaces the old step bands where 74% scored 0.

## Workflow_Templates
Template | Step | Stage (task) | Depends on step | Responsible (R) role | Default R person | R Emp ID | Accountable (A) - exactly one | A Emp ID | Consulted (C) | Informed (I) | Checklist (acceptance criteria) | Reviewer (validation owner) | Review criteria | Required evidence before submit | SLA as written | SLA target (business days) | SLA max (business days) | Effort min (hrs) | Effort max (hrs) | Mitigation | Flags / to confirm
Email campaign | 1 | Campaign request initiation | - | Requesting department (Sales / RMS / Back office / CS / Operations / IT) | Manager of requesting department | (per request) | Marketing POC: Mukesh Thakur |  | - | Email execution: Naveen Kumar | Define campaign objective; Specify target audience; Provide key messages; Share timeline requirements | Manager of requesting department (sheet lists: Gurjot Sodhi - Sales, Kapil Abrol - CS, Pawan Kumar - Operations, Ayushman Dey - RMS, Vivek Sharma - Back office, Rajesh Gaddam - IT, Mukesh Thakur - Marketing) | Request is complete; Fits the marketing calendar | Email request form; Campaign brief document | 2-3 business days | 2 | 3 | 2 | 3 | Assign a backup POC to avoid delays. | Mukesh Thakur is not in the org chart. "Gurjot Sodhi" and "Rajesh Gaddam" do not match org-chart names (Gurjot Singh, AVP-Sales; Patel Rajesh, VP-IT) - confirm. Generic sheet lists Marketing POC as both A and I.
Email campaign | 2 | Content creation | 1 | Content team | Miteeksha | EMP-0153 | Marketing POC: Mukesh Thakur |  | Requesting department | Email execution: Naveen Kumar | Write email copy; Create subject lines; Draft preview text; Include CTA | Content Manager: Miteeksha | Matches the brief; Follows brand guidelines; Proofread | Draft content document; Revision history | 2-3 business days | 2 | 3 | 4 | 8 | Use a content checklist to ensure all requirements are met. | Miteeksha is both the default R and the reviewer - the platform blocks self-review, so assign a different reviewer.
Email campaign | 3 | Content approval | 2 | Content team (routes for sign-off) | Miteeksha | EMP-0153 | Head of requesting department (resolved per request) | (per request) | Compliance team (if needed) | Marketing POC: Mukesh Thakur | Review content accuracy; Check messaging alignment; Verify compliance | Head of requesting department | Department sign-off; Compliance / legal approval; Regulator approval (TRAI or WhatsApp) where needed | Approval email; Change requests | 1-2 business days | 1 | 2 | 2 | 3 | Include a pre-approval review to minimise changes. | Versions disagree: generic sheet says R = Marketing POC and C = Legal team; named sheet says R = Content team and C = Compliance team. A was "Requesting department" (a team) - must be one named person.
Email campaign | 4 | HTML development | 3 | HTML developer | Naveen Kumar | EMP-0118 | Marketing POC: Mukesh Thakur (proposed) |  | Email execution team | Content team; Marketing POC | Code email template; Test responsive design; Optimise for email clients; Include tracking parameters | Proposed: Marketing POC (sheet says HTML developer: Naveen Kumar) | Cross-client testing; Mobile check; Link verification | HTML files; Test screenshots | 1-2 business days | 1 | 2 | 4 | 6 | Test templates on multiple devices and email clients before final approval. | Named sheet makes Naveen Kumar R, A and reviewer - no independent check. Naveen Kumar matches two employees (EMP-0118 Digital Marketing, EMP-0204 RMS) - EMP-0118 assumed.
Email campaign | 5 | Campaign setup and launch | 4 | Email execution team | Naveen Kumar | EMP-0118 | Marketing POC: Mukesh Thakur (proposed) |  | HTML developer | Requesting department; Marketing team | Upload HTML; Import client list; Set up segmentation; Configure tracking; Schedule or launch campaign | Proposed: Marketing POC (sheet says Campaign manager: Naveen Kumar) | Test email send; Verify all links; Check personalisation; Validate list | Test sends; Campaign settings; List verification report | 1-2 business days | 1 | 2 | 3 | 4 | Conduct a dry run before the final launch to identify issues. | Named sheet: Naveen Kumar is R, A, C and reviewer. Highest-risk step (Critical) has no independent check.
Email campaign | 6 | Performance tracking | 5 | Email execution team | Naveen Kumar | EMP-0118 | Marketing POC: Mukesh Thakur (proposed) |  | Data analyst | Requesting department; Marketing team; Stakeholders | Monitor delivery rate; Track open rate; Analyse click rate; Record conversions | Proposed: Data analyst or Marketing POC (sheet says Campaign manager: Naveen Kumar) | Verify tracking setup; Check data accuracy | Campaign analytics; Performance dashboard | Ongoing (initial report 2 days post-launch) | 2 | 2 | 0.5 | 1 | Use automated tools for real-time tracking and reporting. | SLA covers the first report only; the cadence of later reports is not defined. Effort is per report.
|  | End-to-end total (if no step waits) | [13 empty] | 9 | 14 | 15.5 | 25
Source: RACI.xlsx (visible "RACI Matrix" sheet with generic roles, and hidden "Sheet3" with named people). Default people come from the named version; conflicts are in the Flags column. Blue numbers are SLA/effort values taken from the source ranges (target = lower bound, max = upper bound).

## Risk_Register
Risk ID | Template | Step | Stage | Risk | Criticality | Dependencies | Assumptions | Mitigation | Risk owner (Emp ID) | Status | Next review date
RSK-001 | Email campaign | 1 | Campaign request initiation | Incomplete requirements | Medium | Marketing calendar available; Clear business objectives | Requesting team has identified the target audience; Business case is justified | Assign a backup POC to avoid delays. |  | Open
RSK-002 | Email campaign | 1 | Campaign request initiation | Unrealistic timelines | Medium | Marketing calendar available; Clear business objectives | Requesting team has identified the target audience; Business case is justified | Assign a backup POC to avoid delays. |  | Open
RSK-003 | Email campaign | 2 | Content creation | Misalignment with brand voice | High | Complete brief from requesting department; Updated brand guidelines | Content team has capacity; Brand guidelines are current | Use a content checklist to ensure all requirements are met. |  | Open
RSK-004 | Email campaign | 2 | Content creation | Subject-matter expertise gaps | High | Complete brief from requesting department; Updated brand guidelines | Content team has capacity; Brand guidelines are current | Use a content checklist to ensure all requirements are met. |  | Open
RSK-005 | Email campaign | 3 | Content approval | Delayed approvals | High | Content creation completed; Approvers available | Department head has final say; Legal review not always required | Include a pre-approval review to minimise changes. |  | Open
RSK-006 | Email campaign | 3 | Content approval | Multiple revision cycles | High | Content creation completed; Approvers available | Department head has final say; Legal review not always required | Include a pre-approval review to minimise changes. |  | Open
RSK-007 | Email campaign | 4 | HTML development | Rendering issues in email clients | Medium | Final approved content; Email template available | HTML developer has required skills; Email-client list is up to date | Test templates on multiple devices and email clients before final approval. |  | Open
RSK-008 | Email campaign | 4 | HTML development | Broken links or tracking | Medium | Final approved content; Email template available | HTML developer has required skills; Email-client list is up to date | Test templates on multiple devices and email clients before final approval. |  | Open
RSK-009 | Email campaign | 5 | Campaign setup and launch | List quality issues | Critical | Completed HTML; Clean contact list; Approved content | Email platform is functioning; Contact list is up to date | Conduct a dry run before the final launch to identify issues. |  | Open
RSK-010 | Email campaign | 5 | Campaign setup and launch | Technical platform errors | Critical | Completed HTML; Clean contact list; Approved content | Email platform is functioning; Contact list is up to date | Conduct a dry run before the final launch to identify issues. |  | Open
RSK-011 | Email campaign | 6 | Performance tracking | Tracking failures | Low | Tracking implemented correctly; Analytics platform working | Tracking parameters are set correctly; Baseline metrics are established | Use automated tools for real-time tracking and reporting. |  | Open
RSK-012 | Email campaign | 6 | Performance tracking | Data interpretation errors | Low | Tracking implemented correctly; Analytics platform working | Tracking parameters are set correctly; Baseline metrics are established | Use automated tools for real-time tracking and reporting. |  | Open
Source: RACI.xlsx "Risks & Mitigation Strategies". That sheet has no stage column, so risks are mapped to stages by row order (6 rows, 6 stages) - confirm. Each cell held two risks; they are split into one row each. Owner and review date are new fields to fill.

## RCA_Register
RCA ID | Incident title | Product / system | Incident date | Received date | Reported by | Severity | Clients impacted | Orders impacted | Root cause | Root cause category | Gap identified | Correction action taken | Correction completed on | Preventive action | Preventive action owner (Emp ID) | Preventive action due date | Responsible department | Responsible stakeholder (Emp ID) | Expected closure date | Actual closure date | Status | Closure verified by (Emp ID) | Repeat of RCA ID | Individual attribution validated? | Days open (auto) | Closed on time? (auto)
RCA-001 | EXAMPLE - replace or delete: [incident title] | [product / system] | 2026-09-15 | 2026-09-15 | [name or Emp ID] | Medium | [number] | [number] | [what actually caused it] | Process | [which control or check was missing] | [what was done to restore service] | 2026-09-16 | [what will stop it happening again] | [Emp ID] | 2026-09-30 | Client Support | [Emp ID] | 2026-09-30 |  | Preventive action in progress |  |  | No | 14
Note on A1: New: auto-numbered
Note on B1: New
Note on C1: New
Note on D1: New
Note on E1: Source: Received date
Note on F1: New
Note on G1: New: Minor / Medium / Major (same scale as the Compliance KPI)
Note on H1: Source: Total client and order impact (split)
Note on I1: Source: Total client and order impact (split)
Note on J1: Source: Root Cause
Note on K1: New: for trend reporting
Note on L1: Source: Gap Identified
Note on M1: Source: Correction Action taken & Time (split)
Note on N1: Source: Correction Action taken & Time (split)
Note on O1: Source: Preventive Action
Note on P1: New: becomes a task owner in the platform
Note on Q1: New
Note on R1: Source: Responsible Department and Stakeholder (split)
Note on S1: Source: Responsible Department and Stakeholder (split)
Note on T1: Source: Expected date of closure
Note on U1: Source: Actual date of closure
Note on V1: Source: Status (values now defined)
Note on W1: New: closer cannot verify their own RCA
Note on X1: New: links recurring incidents
Note on Y1: New: only "Yes" affects a person's Compliance KPI
Note on Z1: New: formula
Note on AA1: New: formula

## Issue_Register
# | Source | Area | Issue | Severity | Fix Applied / Rule Adopted | Where Fixed
1 | R&R Parameters | Weights | Quantifiable group stated as 60% but its sub-weights sum to 75-100%; Qualitative stated as 40% but sums to 50-65%. | High | 60/40 split retired. Team-category weights are the only weighting model; every category must total exactly 100% (validated on save). | Spec 5.3; Category_Weights
2 | R&R Parameters | Metrics | Core Revenue uses "Culture (10%)", which is not one of the 8 defined metrics. | High | Culture mapped to the Collaboration metric (teamwork, knowledge sharing, conduct). Rubric in Spec 5.2.7. | Spec 5.2.7; Category_Weights
3 | R&R Parameters | Metrics | Productivity is defined but has 0% weight in every category; Innovation appears only in Support. | Medium | Kept as configurable metrics. Productivity is used as an R&R tie-breaker and award input until management assigns it a weight. | Spec 5.3, 7.3
4 | R&R Parameters | Metrics | CSAT has no column in the column definitions; it is folded into "Quality". | Medium | CSAT is a separate metric with its own data source and minimum sample size; Quality no longer contains customer satisfaction. | Spec 5.2.4
5 | R&R Parameters | Categories | Client Support is measured mainly on CSAT, but CSAT is weighted only in Core Revenue. | High | Proposed 4th category "Customer Service" (CSAT 30, Quality 25, On-Time 20, Achievement 15, Compliance 10) - pending approval. | Spec 5.3; Departments
6 | R&R Parameters | Scoring | On-Time bands have a cliff: 75-84% = 3.0 but 74% = 0. | High | Continuous scoring: 95%+ = 100, 85% = 80, 75% = 60, linear between and below (floor 0). Matches every original anchor with no cliff. | Spec 5.2.1; OnTime_Recalc
7 | R&R Parameters | Scoring | Achievement: 100%+ already scores 5.0, so the 150% cap has no effect. | Medium | Meeting target (100%) = 90; over-achievement earns the last 10 points up to the 150% cap = 100. | Spec 5.2.2
8 | R&R Parameters | Scoring | Productivity formula (Output / Team Avg x 5) gives 6.0 at 120%, contradicting its own band (120%+ = 5.0). | Medium | Ratio-based curve capped at 100; weighted by task complexity and adjusted for available capacity; minimum team size 3. | Spec 5.2.6
9 | R&R Parameters | Scoring | Compliance scale stops at 3.0 (one medium incident); multiple or major incidents undefined. | Medium | Deduction model: start 100, Minor -20, Medium -40, Major -100 per validated incident (floor 0). | Spec 5.2.3
10 | R&R Parameters | Scoring | Collaboration and Innovation rubrics define only levels 5 and 3. | Medium | All five levels defined with evidence requirements; scores of 1, 2 and 5 need written evidence. | Spec 5.2.7-5.2.8
11 | R&R Parameters | Scale | Framework scores 1-5; master prompt specifies a 0-100 final score. | Medium | Every metric is computed natively on 0-100. A 1-5 display equivalent = score / 20 is shown for continuity. | Spec 5.1
12 | R&R Parameters | Identity | Framework expects an Emp. ID column; no source file contains employee IDs. | High | Placeholder IDs (EMP-xxxx) issued so records can be linked; HRMS code column added for replacement before go-live. | Employee_Master
13 | Project Tracker | Structure | Three incompatible tracking styles: Product (project = task), CS (same 3 sub-tasks per issue), Ops (task duplicated per person). | High | Normalised to Project > Task > Assignment. CS 3-step pattern becomes a reusable Task Template. | Tracker_Cleaned; Spec 4.7
14 | Project Tracker | Assignees | Multiple people typed into one cell ("Saksham, Jaspreet, Jatin, Aryan, sumit roy"). | High | Split into one assignment row per person with role and contribution % (equal split until confirmed). | Tracker_Cleaned
15 | Project Tracker | Assignees | First names only, inconsistent case and spacing ("pawan", "Vinay "), two names not in the org chart (Ankit Grin, Amandeep). | High | Resolved to Employee IDs with a match note; unresolved names flagged for addition to the master. | Tracker_Cleaned
16 | Project Tracker | Priority | Priority blank on all 74 Customer Support rows. | High | Priority is mandatory at project level; missing values flagged yellow for the owner to set. | Project_Register
17 | Project Tracker | Deadlines | 80 of 115 rows have no usable target date (68 blank, 12 contain "-"). | High | Text dashes cleared; rows without a deadline are shown as "No deadline" and are not eligible for On-Time. | Tracker_Cleaned
18 | Project Tracker | Dates | Completed date 13-Oct-2026 recorded for "Account opening journey with (AI)", which is in the future. | High | Flagged; platform blocks completion dates later than today. | Tracker_Cleaned; Spec P7
19 | Project Tracker | Status | 8 projects have a completed date while status is On Hold / In Review / Ongoing; 2 are Completed with no date. | High | Only status Completed with a completion date counts as completed. Completed-without-date moved to In Review. | Tracker_Cleaned
20 | Project Tracker | Status | "Delayed" used as a manual status, while genuinely late tasks sit in other statuses. | High | Delayed removed as a status and derived from dates (Late / Overdue). Delayed rows mapped to Blocked or In Progress by blocker type. | Tracker_Cleaned; Spec 4.3
21 | Project Tracker | Status | Customer Support items opened in Nov 2024 are still "Ongoing". | Medium | Flagged "Open > 6 months"; platform raises stale-task alerts after a configurable number of days. | Tracker_Cleaned; Spec P8
22 | Project Tracker | Blockers | Delay reasons are free text; about half point to Product/Development dependency. | Medium | Classified into blocker types (dependency, reprioritisation, requirement change, technical, rework). | Tracker_Cleaned; Spec 4.5
23 | Project Tracker | Teams | Team names do not match the org chart (Customer Support vs Client Support, Operations vs Back ofc & Operations, Finance vs Accounts). | Medium | Canonical department list with alias mapping. | Departments
24 | Project Tracker | Data | Stray value "Learning & Development" at row 1,048,450 inflates the used range to 1M rows. | Low | Ignored during migration. | Tracker_Cleaned
25 | Project Tracker | Formulas | Dashboard and R&R formulas only cover rows 4-25, so they count 22 of 115 rows (Product only). | High | All calculations use full ranges; platform computes from the database, not fixed ranges. | OnTime_Recalc
26 | Project Tracker | Formulas | Rewards Snapshot counts the "Reward Given" column for rows 4-7 instead of "Reward Tier" - always 0. | Medium | Replaced by R&R dashboard reading award records. | Spec P13
27 | Project Tracker | Formulas | Cell K39 has a broken reference (REF error); On Hold count starts at row 5; row 7 counts by Champion instead of Team Member. | Medium | Superseded by recalculated sheets. | OnTime_Recalc
28 | Project Tracker | R&R logic | Validated delays still counted as late (e.g., SensAI delayed by management reprioritisation, validated Yes). | High | Late tasks with a validated, excludable blocker are removed from the On-Time denominator. | OnTime_Recalc; Spec 5.2.1
29 | Project Tracker | R&R logic | On Hold tasks with a completed date counted as on-time completions (Shoonya R&R, Jumpp Website 1.1). | High | Only Completed status counts. | OnTime_Recalc
30 | Project Tracker | R&R logic | "Tasks Delayed" counts only status = Delayed, so late tasks in other statuses show 0. | High | Lateness derived from dates. | Tracker_Cleaned
31 | Project Tracker | R&R logic | Points formula yields at most 10 without manual bonus; Gold 50 / Silver 30 / Bronze 15 are only reachable through bonus points. | High | Points and free bonus removed. Tiers based on the 0-100 performance score plus eligibility gates; recognition by evidence-backed nomination. | Spec 7
32 | Project Tracker | R&R logic | Column labelled "SLA / TAT Compliance" actually computes on-time rate. | Low | Renamed On-Time Rate. | OnTime_Recalc
33 | Org Chart | Format | Hierarchy stored as SmartArt diagrams, not data; cannot be imported directly. | High | All 325 boxes extracted into a flat Employee_Master with manager links. | Employee_Master
34 | Org Chart | Versions | Hidden sheets "Prodduct" and "Product-Shoonya" are outdated Product charts. | Medium | Excluded; only the visible Products sheet imported. | Employee_Master
35 | Org Chart | Identity | 16 names are shared by more than one record (e.g., two Pawan Kumars, Amit Kumars, Mukesh Kumars). | High | Each record has its own ID; collisions listed for HR confirmation. | Name_Collisions
36 | Org Chart | Duplicates | Salim Khan appears twice under the same RMS manager; Amritpal Singh twice in Client Support. | Medium | Flagged as possible duplicates pending confirmation. | Name_Collisions
37 | Org Chart | Positions | Vacant or unnamed boxes (Managing Director, Head Insurance, AM Compliance, Front Desk head, an empty HR box). | Medium | Position entity separated from Employee; vacancies imported as POS- records. | Employee_Master; Spec 3
38 | Org Chart | Heads | Pawan Kumar (AVP-Operations) heads Demat, Operations & BO and Compliance. | Medium | HOD can own multiple departments; one person record, several department-head links. | Employee_Master; Spec 2
39 | Org Chart | Names | Informal or incomplete names ("Ramneek Mam", single names, malformed brackets, typos in designations). | Low | Cleaned; single-name records flagged for surname. | Employee_Master
40 | Org Chart | Matrix | People report into one department but work on another's projects (e.g., Associate BAs under Sales working on Product). | Medium | Reporting manager (HR line) and project membership (work line) kept separate; visibility granted through both. | Spec 2.3
41 | Master Prompt | Categories | No mapping of the 17 departments to performance categories. | High | Proposed mapping with team-level overrides (NBFC, jUMPP, RMS & Dealer). | Departments; Spec 5.4
42 | Master Prompt | Data sources | Only On-Time can be derived today; Achievement, CSAT, Compliance and Quality have no source. | High | Source and entry method defined per metric; missing metrics renormalised if at least 70% of weight has data, else Insufficient Data. | Spec 5.5
43 | Master Prompt | Access | "Team login" implies shared credentials, which breaks the audit trail. | High | Named individual accounts only; no shared logins. | Spec 2.1
44 | Master Prompt | Access | With no employee logins, managers must enter every update for about 317 people. | Medium | Team Lead role made standard (update rights on own team tasks); bulk update and CSV import provided. | Spec 2.1, P7
45 | Master Prompt | Visibility | Strict team-only visibility hides cross-team blockers (CS projects waiting on Product). | High | Visibility = own hierarchy + projects you own or are a member of + read-only view of blocking tasks. | Spec 2.2
46 | Master Prompt | Attribution | No rule for credit/blame on multi-assignee tasks. | High | Assignment records with role (Owner/Contributor) and contribution % summing to 100%. | Spec 4.6
47 | RACI | Versions | Two versions of the matrix: the visible sheet uses generic roles, a hidden "Sheet3" has named people, and they disagree (e.g. Content approval R = Marketing POC vs Content team; Legal vs Compliance). Mitigations sit in a separate block in the visible sheet. | Medium | Template stores roles with a default person; named version used for defaults; every conflict flagged for confirmation. | Workflow_Templates
48 | RACI | Accountability | Content approval has A = "Requesting department" - a team, not one person. | High | Every step must have exactly one named Accountable; for request-driven steps it resolves to the head of the requesting department when the request is raised. | Workflow_Templates; CLAUDE.md
49 | RACI | Separation of duties | Steps 4-6: Naveen Kumar is Responsible, Accountable, Consulted and validation owner - nobody independently checks the Critical-risk launch step. | High | Platform blocks reviewing your own work; a different validation owner is proposed (Marketing POC or Data analyst). | Workflow_Templates
50 | RACI | Redundancy | Same person holds two letters on one step (Marketing POC is A and I on step 1; C = R on steps 5-6). | Low | One letter per person per step; duplicates removed. | Workflow_Templates
51 | RACI | SLA | SLAs are text ranges ("2-3 business days"); performance tracking is "Ongoing" with only the first report timed. | Medium | Stored as target and max business days; due date uses the max, working-day calendar applied; cadence for later reports to be defined. | Workflow_Templates
52 | RACI | People | Mukesh Thakur (Marketing POC) is not in the org chart; "Gurjot Sodhi" and "Rajesh Gaddam" do not match org-chart names; Naveen Kumar matches two employees. | High | Flagged; people are linked by Emp ID once confirmed. | Workflow_Templates; Name_Collisions
53 | RACI | Risks | Risk sheet has no stage column, two risks per cell, no owner or status, and a trailing empty header row. | Medium | Mapped to stages by row order (confirm); one risk per row; owner, status and review date added. | Risk_Register
54 | RCA | Template | Template has headers only - no ID, incident date, product, severity, owner or defined status values. | High | RCA register with auto ID, severity (same scale as the Compliance KPI), root-cause category, owners as Emp IDs and a status list. | RCA_Register
55 | RCA | Combined fields | "Correction action taken & time", "Total client and order impact" and "Responsible department and stakeholder" each hold two values. | Medium | Split into separate columns so they can be filtered, validated and reported. | RCA_Register
56 | RCA | Preventive actions | Preventive action has no owner or due date, so it cannot be tracked to completion. | High | Owner and due date added; in the platform each preventive action becomes a task, and the RCA closes only when those tasks are accepted and closure is verified by someone else. | RCA_Register; CLAUDE.md
57 | RCA | Fairness | No rule for how an incident affects an individual's performance. | High | An incident counts against a person's Compliance KPI only when severity and individual attribution are both validated; otherwise it is a department-level metric. | CLAUDE.md
58 | RCA | Formatting | Sheet is formatted to W983 for 10 header cells (73 KB). | Low | Ignored on import. | RCA_Register