## Project & Task Tracker
PROJECT & TASK TRACKER
Project / Initiative | Task / Deliverable | Team Member | Team | Champion / Owner | Priority | Start Date | Target Date | Completed Date | Status | On Time? (auto) | Delay Reason | Delay Reason Validated? | Remarks | Monthly Individual Target (Number) | Monthly Achieved (Number) | Achievement % (auto)
Sales Performance | Call Volume 200 Calls Per Day | Babita | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 |  | Completed |  |  |  |  | 4400 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Babita | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 |  | Ongoing |  |  |  |  | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Babita | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 |  | Ongoing |  |  |  |  | 440 |  | 0%
Sales Performance | Call Volume 200 Calls Per Day | Kulwinder | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 4400 | 4000 | 91%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Kulwinder | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Kulwinder | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 440 |  | 0%
Sales Performance | Call Volume 194 Calls Per Day | Rahul | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4268 |  | 0%
Sales Performance | Client Interaction 97 Calls Per Day (50% of Calls Done) | Rahul | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2134 |  | 0%
Sales Performance | Accounts Target Monthly 400 Accounts | Rahul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 400 |  | 0%
Sales Performance | Call Volume 200 Calls Per Day | Nadeem | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4400 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Nadeem | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Nadeem | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 440 |  | 0%
Sales Performance | Call Volume 200 Calls Per Day | Upasana | Sales |  | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4400 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Upasana | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Upasana | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 440 |  | 0%
Sales Performance | Call Volume 180 Calls Per Day | Anshul | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3960 |  | 0%
Sales Performance | Client Interaction 72 Calls Per Day (40% of Calls Done) | Anshul | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 1584 |  | 0%
Sales Performance | Accounts Target Monthly 390 Accounts | Anshul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 390 |  | 0%
Sales Performance | Call Volume 200 Calls Per Day | Alishba | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4400 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Alishba | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Alishba | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 440 |  | 0%
Sales Performance | Call Volume 200 Calls Per Day | Rajat | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4400 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Rajat | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Rajat | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 440 |  | 0%
Sales Performance | Call Volume 200 Calls Per Day | Ujjwala | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4400 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day (50% of Calls Done) | Ujjwala | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Accounts Target Monthly 440 Accounts | Ujjwala | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 440 |  | 0%
Sales Performance | Call Volume 150 Calls Per Day | Ramandeep | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Client Interaction 60 Calls Per Day (40% of Calls Done) | Ramandeep | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 1320 |  | 0%
Sales Performance | Accounts Target Monthly 330 Accounts | Ramandeep | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Call Volume 190 Calls Per Day | Tanu | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 4180 | 4000 | 96%
Sales Performance | Client Interaction 85 Calls Per Day (45% of Calls Done) | Tanu | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 1881 |  | 0% | 32
Sales Performance | Accounts Target Monthly 410 Accounts | Tanu | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 410 |  | 0%
Sales Performance | Call Volume 150 Calls Per Day | Sakshi | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 3300 |  | 0%
Sales Performance | Client Interaction 60 Calls Per Day (40% of Calls Done) | Sakshi | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 1320 |  | 0%
Sales Performance | Accounts Target Monthly 300 Accounts | Sakshi | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | 300 |  | 0%
Sales Performance | Team Call Volume 200 Calls Per Day | Rajesh | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 49808 | 50000 | 100%
Sales Performance | Team Client Interaction 100 Calls Per Day (50% of Calls Done) | Rajesh | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 23639 | 25000 | 106%
Sales Performance | Team Accounts Target Monthly 440 Accounts | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | 2026-09-30 | Completed | Yes |  |  |  | 4910 | 7000 | 143%
Sales Performance | Overall Accounts Conversion | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | NA (40% Of Leads)
Sales Performance | Team Call Volume 185 Calls Per Day | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 4080 |  | 0%
Sales Performance | Team Client Interaction 90 Calls Per Day (50% of Calls Done) | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 1980 |  | 0%
Sales Performance | Team Accounts Target Monthly 350 Accounts | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 350 |  | 0%
Sales Performance | Call Volume 110 Calls Per Day | Deepak Moraina | Sales | Durga | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2420 |  | 0%
Sales Performance | Client Intraction 50 call per day (35 % call done ) | Deepak Moraina | Sales | Durga | High | 2026-09-01 | 2026-09-30 | [6 empty] | 1100 |  | 0%
Sales Performance | Account Opening Targets | Deepak Moraina | Sales | Durga | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Team Call Volume 211 Calls Per Day | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 4642 |  | 0%
Sales Performance | Team Client Interaction 106 Calls Per Day (50% of Calls Done) | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2332 |  | 0%
Sales Performance | Team Accounts Target Monthly 264 Accounts | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 264 |  | 0%
Sales Performance | Lead-to-Registration Conversion Performance (Team) | Anju Kumari | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | NA (40% Of Leads)
Sales Performance | Call Volume 136 Calls Per Day | Neha Solanki | Sales | Anju Kumari | High | 2026-09-01 | 2026-09-30 | [6 empty] | 3000 |  | 0%
Sales Performance | Client Interaction 80 Calls Per Day (58% of Calls Done) | Neha Solanki | Sales | Anju Kumari | High | 2026-09-01 | 2026-09-30 | [6 empty] | 1800 |  | 0%
Sales Performance | Accounts Target Monthly 250 Accounts(42% of Lead) | Neha Solanki | Sales | Anju Kumari | High | 2026-09-01 | 2026-09-30 | [6 empty] | 250 |  | 0%
Sales Performance | Call Volume 185 Calls Per Day | Shivani Sharma | Sales | Amit Kumar | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4070 |  | 0%
Sales Performance | Client Interaction 150 Calls Per Day | Shivani Sharma | Sales | Amit Kumar | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Funded Clients Target Monthly 330 Accounts | Shivani Sharma | Sales | Amit Kumar | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Fundes Added Target Monthly 2 cr Accounts | Shivani Sharma | Sales | Amit Kumar | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2 cr
Sales Performance | Call Volume 185 Calls Per Day | Shivani. D | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4070 |  | 0%
Sales Performance | Client Interaction 150 Calls Per Day | Shivani. D | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Funded Clients Target Monthly 330 Accounts | Shivani. D | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Fundes Added Target Monthly 2 cr Accounts | Shivani. D | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2 cr
Sales Performance | Call Volume 150 Calls Per Day | Shubham | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Client Interaction 125 Calls Per Day | Shubham | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2750 |  | 0%
Sales Performance | Account Reactivation Target Monthly 50 Accounts | Shubham | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 50 |  | 0%
Sales Performance | Fundes Added Target Monthly 10 Lacs Accounts | Shubham | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 10 lacs
Sales Performance | Call Volume 150 Calls Per Day | Simar | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Client Interaction 125 Calls Per Day | Simar | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2750 |  | 0%
Sales Performance | Account Reactivation Target Monthly 50 Accounts | Simar | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 50 |  | 0%
Sales Performance | Fundes Added Target Monthly 10 Lacs Accounts | Simar | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 10 lacs
Sales Performance | Call Volume 150 Calls Per Day | Anita | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Client Interaction 125 Calls Per Day | Anita | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2750 |  | 0%
Sales Performance | Account Reactivation Target Monthly 50 Accounts | Anita | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 50 |  | 0%
Sales Performance | Fundes Added Target Monthly 10 Lacs Accounts | Anita | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 10 lacs
Sales Performance | Call Volume 150 Calls Per Day | Parmodh | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Client Interaction 90 Calls Per Day | Parmodh | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 1980 |  | 0%
Sales Performance | Funded Clients Target Monthly 660 Accounts | Parmodh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 660 |  | 0%
Sales Performance | Fundes Added Target Monthly 3.40 cr Accounts | Parmodh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 3.40 cr
Sales Performance | Call Volume 150 Calls Per Day | Amanpreet | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Client Interaction 90 Calls Per Day | Amanpreet | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 1980 |  | 0%
Sales Performance | Funded Clients Target Monthly 660 Accounts | Amanpreet | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 660 |  | 0%
Sales Performance | Fundes Added Target Monthly 3.40 cr Accounts | Amanpreet | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 3.40 cr
Sales Performance | Call Volume 175 Calls Per Day | Satwinder | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3850 |  | 0%
Sales Performance | Client Interaction 100 Calls Per Day | Satwinder | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2200 |  | 0%
Sales Performance | Funded Clients Target Monthly 660 Accounts | Satwinder | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 660 |  | 0%
Sales Performance | Fundes Added Target Monthly 3.40 cr Accounts | Satwinder | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 3.40 cr
Sales Performance | Call Volume 185 Calls Per Day | Gouri | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4070 |  | 0%
Sales Performance | Client Interaction 130 Calls Per Day | Gouri | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 2860 |  | 0%
Sales Performance | Funded Clients Target Monthly 660 Accounts | Gouri | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 660 |  | 0%
Sales Performance | Fundes Added Target Monthly 3.40 cr Accounts | Gouri | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 3.40 cr
Sales Performance | Call Volume 185 Calls Per Day | Ashwani | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4070 |  | 0%
Sales Performance | Client Interaction 150 Calls Per Day | Ashwani | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Funded Clients Target Monthly 330 Accounts | Ashwani | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Fundes Added Target Monthly 2 cr Accounts | Ashwani | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2 cr
Sales Performance | Call Volume 185 Calls Per Day | Shalini | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4070 |  | 0%
Sales Performance | Client Interaction 150 Calls Per Day | Shalini | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Funded Clients Target Monthly 330 Accounts | Shalini | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Fundes Added Target Monthly 2 cr Accounts | Shalini | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2 cr
Sales Performance | Call Volume 185 Calls Per Day | Salamat | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 4070 |  | 0%
Sales Performance | Client Interaction 150 Calls Per Day | Salamat | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 3300 |  | 0%
Sales Performance | Funded Clients Target Monthly 330 Accounts | Salamat | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 330 |  | 0%
Sales Performance | Fundes Added Target Monthly 2 cr Accounts | Salamat | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 2 cr
Sales Performance | Team Call Volume | Amit | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 44000 |  | 0%
Sales Performance | Team Client Interaction | Amit | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30 | [6 empty] | 32890 |  | 0%
Sales Performance | Zero-Funded Clients | Amit | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 4290 |  | 0%
Sales Performance | Fundes Added | Amit | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 236000000 |  | 0%
Sales Performance | Account Reactivation | Amit | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 150 |  | 0%
Sales Performance | Fundes Added | Amit | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30 | [6 empty] | 3500000 |  | 0%
Sales Performance | HNI Client - Resolve client issues | Amit | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30

## Rewards & Recognition
REWARDS & RECOGNITION
Team Member | Team | Tasks Completed On Time (auto) | Tasks Delayed (auto) | Avg Achievement % (auto) | Avg Quality | Csat | Compliance | Innovation | Bonus Points (you type this) | Total Points (auto) | Reward Tier (auto) | Reward Given | Date Awarded | Approved By
Babita | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Kulwinder | #VALUE! | 1 | 0 | [6 empty] | 0 | No Reward Yet
Rahul | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Nadeem | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Upasana | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Anshul | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Alishba | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Rajat | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Ujjwala | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Ramandeep | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Tanu | Sales | 3 | 0 | [6 empty] | 0 | No Reward Yet
Sakshi | Sales | 1 | 0 | [6 empty] | 0 | No Reward Yet
Rajesh | Sales | 3 | 0 | [6 empty] | 0 | No Reward Yet
Durga | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Deepak Moraina | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Anju Kumari | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Neha Solanki | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Pramodh | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Amanpreet | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Satwinder | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Gouri | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Ashwani | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Shalini | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Salamat | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Shivani Sharma | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Shivani Dhiman | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Shubham | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Simar | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Anita | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet
Amit | Sales | 0 | 0 | [6 empty] | 0 | No Reward Yet

## Dashboard
TEAM & PROJECT DASHBOARD
Live — updates automatically from the other 3 sheets
Total Tasks | Ongoing | Completed | Delayed
91 | 2 | 9 | 0
Task Status | Count |  | Team | Open Tasks
Ongoing | 2 |  | Learning & Development | 0
Completed | 9 |  | Human Resources | 0
Delayed | 0 |  | IT / Tech | 0
On Hold | 0 |  | Sales | 82
|  |  | Operations | 0
|  |  | Compliance | 0
|  |  | Customer Support | 0
|  |  | Finance | 0
REWARDS SNAPSHOT
Gold | 0
Silver | 0
Bronze | 0

## Extra Tasks
Project / Initiative | Task / Deliverable | Team Member | Team | Champion / Owner | Priority | Start Date | Target Date | Completed Date | Status | On Time? (auto) | Delay Reason | Delay Reason Validated? | Remarks | Monthly Individual Target (Number) | Monthly Achieved (Number) | Achievement % (auto)
Sales Performance | Backstage, Hold, Chat, Star ticket etc other tasks completion on daily basis | Sakshi | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | Update within within TAT Star (within hour) same day
Sales Performance | Team Audit | Sakshi | Sales | Rajesh | High | 2026-09-01 | 2026-09-30 | [6 empty] | Monthly
Sales Performance | Team Tasks Audit | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Daily & Monthly Tasks & Report Updation | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Internal & External Meetings | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Requirements Through Jira | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Onboarding & Other Enhancements | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Testing & Feedback Etc | Rajesh | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Non-Individual Account Opening Conversion | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Fund Mobilisation from Existing Active Non-Individual Clients – Daily checking by Back Office | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | New AP Onboarding (Acquire and successfully onboard new Authorized Partners by completing documentation, activation, and training processes within the defined timelines. | Durga | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30
Sales Performance | Lead-to-Registration Conversion Performance (Team) | Durga | Sales | Gurjot Sodhi | Medium | 2026-09-01 | 2026-09-30
Sales Performance | Team Productivity & Target Achievement (Drive timely achievement of team targets by enhancing overall productivity through performance tracking, gap analysis, and strong accountability.) | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Daily & Monthly Tasks & Report Updation | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Internal & External Meetings | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Requirements Through Jira | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Onboarding Enhancements | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Testing & Feedback Etc | Durga | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Physical Form Filling | Deepak Moraina | Sales | Durga | High | 2026-09-01 | 2026-09-30
Sales Performance | Physical Form Collection/Verification – NRI Form, Joint Account & Minor Account with Anju | Deepak Moraina | Sales | Durga | High | 2026-09-01 | 2026-09-30
Sales Performance | IPV Process Management | Deepak Moraina | Sales | Durga | High | 2026-09-01 | 2026-09-30
Sales Performance | NRI Account Opening Conversion | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Fund Mobilisation from Existing Active NRl Clients – Daily checking by Back Office | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Individual Account Opening Conversion | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | HNI Client Service Excellence | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Sales Incoming Call Handling | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Team Productivity & Target Achievement (Drive timely achievement of team targets by enhancing overall productivity through performance tracking, gap analysis, and strong accountability.) | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Daily & Monthly Tasks & Report Updation | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Internal & External Meetings | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Onboarding Enhancements | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Testing & Feedback Etc | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Courier ticket and Star ticket etc other tasks completion on daily basis | Anju Kumari | Sales | Gurjot Sodhi | High | 2026-09-01 | 2026-09-30
Sales Performance | Missing Tickets to maintain lower backlog | Rahul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30
Sales Performance | Testing & Feedback Etc | Rahul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30
Sales Performance | Team Audit | Anshul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30
Sales Performance | Esign Check | Anshul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30
Sales Performance | Testing & Feedback Etc | Anshul | Sales | Rajesh | High | 2026-09-01 | 2026-09-30
Sales Performance | Reception Tasks Are Being Handled Efficiently | Ramandeep | Sales | Rajesh | Medium | 2026-09-01 | 2026-09-30